## Raw_Data
program_id | program_name | customer_type | program_type | program_manager | reporting_month | cost_category | budget_cost | actual_cost | earned_value | forecast_cost | budget_variance | budget_variance_pct | cost_variance | cpi
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-01-01 | Labor | 505854.82 | 510165.41 | 510925.25 | 511260.44 | 4310.59 | 0.8521% | 759.84 | 1.0015
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-01-01 | Materials | 410890.08 | 417855.42 | 416961.97 | 418271.21 | 6965.34 | 1.695% | -893.45 | 0.99786
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-01-01 | Subcontracts | 323406.43 | 324093.65 | 317411.56 | 326296.41 | 687.22 | 0.2125% | -6682.09 | 0.97938
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-01-01 | Overhead | 222380.87 | 225837.17 | 217884.41 | 223467.47 | 3456.3 | 1.554% | -7952.76 | 0.96479
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-01-01 | Travel | 55834.05 | 54252.57 | 55320.74 | 55545.71 | -1581.48 | -2.832% | 1068.17 | 1.0197
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-01-01 | Other Direct Costs | 84721.4 | 84394.25 | 84535.55 | 85484.36 | -327.15 | -0.3861% | 141.3 | 1.0017
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-02-01 | Labor | 497458.24 | 497706.1 | 492186.46 | 499788.82 | 247.86 | 0.04983% | -5519.64 | 0.98891
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-02-01 | Materials | 417224.61 | 428145.64 | 420001.51 | 422933.18 | 10921.03 | 2.618% | -8144.13 | 0.98098
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-02-01 | Subcontracts | 315306.42 | 323662.89 | 308232.4 | 323866.7 | 8356.47 | 2.65% | -15430.49 | 0.95233
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-02-01 | Overhead | 239542.09 | 240283.96 | 233770.09 | 239579.57 | 741.87 | 0.3097% | -6513.87 | 0.97289
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-02-01 | Travel | 54895.05 | 56272.67 | 54400.57 | 55559.91 | 1377.62 | 2.51% | -1872.1 | 0.96673
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-02-01 | Other Direct Costs | 85923.92 | 83667.24 | 83509.38 | 83455.33 | -2256.68 | -2.626% | -157.86 | 0.99811
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-03-01 | Labor | 514395.86 | 520812.76 | 523075.54 | 512596.9 | 6416.9 | 1.247% | 2262.78 | 1.0043
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-03-01 | Materials | 421824.89 | 430323.84 | 421108.62 | 426907.83 | 8498.95 | 2.015% | -9215.22 | 0.97859
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-03-01 | Subcontracts | 324356.22 | 325160.72 | 329633.02 | 327871.5 | 804.5 | 0.248% | 4472.3 | 1.0138
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-03-01 | Overhead | 228419.51 | 226332.14 | 230282.18 | 226796.72 | -2087.37 | -0.9138% | 3950.04 | 1.0175
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-03-01 | Travel | 57291.57 | 56301.03 | 56998.92 | 57086.98 | -990.54 | -1.729% | 697.89 | 1.0124
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-03-01 | Other Direct Costs | 89609.18 | 92312.21 | 88651.78 | 91973.9 | 2703.03 | 3.016% | -3660.43 | 0.96035
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-04-01 | Labor | 522975.9 | 514375.3 | 519643.13 | 513202.88 | -8600.6 | -1.645% | 5267.83 | 1.0102
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-04-01 | Materials | 410686.58 | 412296.36 | 406669.96 | 413491.31 | 1609.78 | 0.392% | -5626.4 | 0.98635
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-04-01 | Subcontracts | 325888.64 | 315043.23 | 317340.94 | 315914.07 | -10845.41 | -3.328% | 2297.71 | 1.0073
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-04-01 | Overhead | 235828.68 | 229294.68 | 235266.4 | 234773.17 | -6534 | -2.771% | 5971.72 | 1.026
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-04-01 | Travel | 57758.86 | 59104.31 | 58170.65 | 59010.05 | 1345.45 | 2.329% | -933.66 | 0.9842
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-04-01 | Other Direct Costs | 87110.96 | 84474.43 | 85229.95 | 86481.65 | -2636.53 | -3.027% | 755.52 | 1.0089
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-05-01 | Labor | 511103.16 | 503460.05 | 512990.12 | 501109.24 | -7643.11 | -1.495% | 9530.07 | 1.0189
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-05-01 | Materials | 426203.03 | 417234.5 | 427453.16 | 425997.94 | -8968.53 | -2.104% | 10218.66 | 1.0245
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-05-01 | Subcontracts | 329654.74 | 330396.67 | 336120.86 | 329691.16 | 741.93 | 0.2251% | 5724.19 | 1.0173
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-05-01 | Overhead | 234956.57 | 229783.92 | 228757.15 | 230925.63 | -5172.65 | -2.202% | -1026.77 | 0.99553
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-05-01 | Travel | 57182.78 | 55323.97 | 57177.69 | 56113.36 | -1858.81 | -3.251% | 1853.72 | 1.0335
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-05-01 | Other Direct Costs | 85237.99 | 87553.91 | 83729.62 | 87135.62 | 2315.92 | 2.717% | -3824.29 | 0.95632
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-06-01 | Labor | 520154.84 | 519136.11 | 516890.56 | 521661.8 | -1018.73 | -0.1959% | -2245.55 | 0.99567
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-06-01 | Materials | 431555.51 | 418452.58 | 425703.83 | 429929.25 | -13102.93 | -3.036% | 7251.25 | 1.0173
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-06-01 | Subcontracts | 321989.65 | 313447.44 | 330216.91 | 321908.76 | -8542.21 | -2.653% | 16769.47 | 1.0535
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-06-01 | Overhead | 241495.59 | 245066.44 | 238843.96 | 246724.12 | 3570.85 | 1.479% | -6222.48 | 0.97461
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-06-01 | Travel | 58841.84 | 58516.03 | 60316 | 58695.81 | -325.81 | -0.5537% | 1799.97 | 1.0308
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-06-01 | Other Direct Costs | 89330.08 | 91408.73 | 90894.76 | 89750.37 | 2078.65 | 2.327% | -513.97 | 0.99438
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-07-01 | Labor | 559388.72 | 560177.17 | 555331.19 | 566508.91 | 788.45 | 0.1409% | -4845.98 | 0.99135
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-07-01 | Materials | 411616.84 | 402823.97 | 421680.29 | 411669.31 | -8792.87 | -2.136% | 18856.32 | 1.0468
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-07-01 | Subcontracts | 346149.09 | 337261.28 | 336526.16 | 345721.21 | -8887.81 | -2.568% | -735.12 | 0.99782
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-07-01 | Overhead | 251219.81 | 252641.8 | 251533.08 | 253665.37 | 1421.99 | 0.566% | -1108.72 | 0.99561
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-07-01 | Travel | 57649.01 | 57566.71 | 56720.65 | 57278.23 | -82.3 | -0.1428% | -846.06 | 0.9853
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-07-01 | Other Direct Costs | 88532.49 | 88318.64 | 88186.08 | 88008.32 | -213.85 | -0.2415% | -132.56 | 0.9985
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-08-01 | Labor | 523100.62 | 520954.31 | 519103.98 | 528867.1 | -2146.31 | -0.4103% | -1850.33 | 0.99645
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-08-01 | Materials | 418447.48 | 416893.1 | 415038.37 | 414772.17 | -1554.38 | -0.3715% | -1854.73 | 0.99555
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-08-01 | Subcontracts | 327620.29 | 327411.44 | 319555.43 | 331054.58 | -208.85 | -0.06375% | -7856.01 | 0.97601
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-08-01 | Overhead | 255203.57 | 250375.57 | 253471.01 | 254911.46 | -4828 | -1.892% | 3095.44 | 1.0124
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-08-01 | Travel | 57569.76 | 57434.02 | 56278.41 | 58360.41 | -135.74 | -0.2358% | -1155.61 | 0.97988
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-08-01 | Other Direct Costs | 94021.06 | 93609.14 | 93736.4 | 95319.99 | -411.92 | -0.4381% | 127.26 | 1.0014
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-09-01 | Labor | 555166.69 | 552090.7 | 546056.05 | 562068.18 | -3075.99 | -0.5541% | -6034.65 | 0.98907
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-09-01 | Materials | 442161.22 | 437140.08 | 446544.05 | 445873.7 | -5021.14 | -1.136% | 9403.97 | 1.0215
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-09-01 | Subcontracts | 347168.22 | 340255.97 | 355124.99 | 345792.35 | -6912.25 | -1.991% | 14869.02 | 1.0437
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-09-01 | Overhead | 252023.97 | 249234.32 | 245502.34 | 249058.81 | -2789.65 | -1.107% | -3731.98 | 0.98503
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-09-01 | Travel | 59116.46 | 57109 | 60788.76 | 57869.91 | -2007.46 | -3.396% | 3679.76 | 1.0644
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-09-01 | Other Direct Costs | 94941.9 | 97298.54 | 93825.27 | 96454.96 | 2356.64 | 2.482% | -3473.27 | 0.9643
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-10-01 | Labor | 537089.14 | 549417.59 | 545851.88 | 544108.36 | 12328.45 | 2.295% | -3565.71 | 0.99351
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-10-01 | Materials | 424553.65 | 434834.86 | 424811.36 | 426744.51 | 10281.21 | 2.422% | -10023.5 | 0.97695
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-10-01 | Subcontracts | 355108.36 | 348800.59 | 344647.85 | 348909.63 | -6307.77 | -1.776% | -4152.74 | 0.98809
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-10-01 | Overhead | 258241.88 | 266087.89 | 250940.82 | 264949.22 | 7846.01 | 3.038% | -15147.07 | 0.94307
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-10-01 | Travel | 59930.9 | 61846.04 | 61029.37 | 60878.8 | 1915.14 | 3.196% | -816.67 | 0.9868
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-10-01 | Other Direct Costs | 95161.94 | 96512.35 | 95151.78 | 96208.22 | 1350.41 | 1.419% | -1360.57 | 0.9859
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-11-01 | Labor | 562052.06 | 558621.54 | 564778.72 | 562707.27 | -3430.52 | -0.6104% | 6157.18 | 1.011
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-11-01 | Materials | 425276.98 | 411582.33 | 413153.7 | 418677.56 | -13694.65 | -3.22% | 1571.37 | 1.0038
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-11-01 | Subcontracts | 333564.6 | 344000.08 | 329431.42 | 344671.06 | 10435.48 | 3.128% | -14568.66 | 0.95765
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-11-01 | Overhead | 261792.25 | 265816.57 | 267079.61 | 267897.05 | 4024.32 | 1.537% | 1263.04 | 1.0048
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-11-01 | Travel | 58896.08 | 57526.72 | 57145.65 | 57829.93 | -1369.36 | -2.325% | -381.07 | 0.99338
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-11-01 | Other Direct Costs | 94210.56 | 93984.56 | 91476.06 | 94120.01 | -226 | -0.2399% | -2508.5 | 0.97331
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-12-01 | Labor | 554636.62 | 561463.57 | 570835.25 | 557137.9 | 6826.95 | 1.231% | 9371.68 | 1.0167
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-12-01 | Materials | 456922.56 | 471107.35 | 461562.71 | 461749.42 | 14184.79 | 3.104% | -9544.64 | 0.97974
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-12-01 | Subcontracts | 345650.74 | 345117.49 | 355736.1 | 348994.54 | -533.25 | -0.1543% | 10618.61 | 1.0308
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-12-01 | Overhead | 256724.91 | 255327.71 | 255112.42 | 257520.15 | -1397.2 | -0.5442% | -215.29 | 0.99916
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-12-01 | Travel | 62620.91 | 64701.36 | 61516.74 | 63346.69 | 2080.45 | 3.322% | -3184.62 | 0.95078
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2024-12-01 | Other Direct Costs | 93596.97 | 90345.17 | 94186.37 | 92964.99 | -3251.8 | -3.474% | 3841.2 | 1.0425
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-01-01 | Labor | 525024.01 | 524418.84 | 539171.92 | 518599.46 | -605.17 | -0.1153% | 14753.08 | 1.0281
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-01-01 | Materials | 427920.16 | 421359.52 | 417268.53 | 430651.04 | -6560.64 | -1.533% | -4090.99 | 0.99029
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-01-01 | Subcontracts | 318166.36 | 310211.42 | 310004.67 | 310004 | -7954.94 | -2.5% | -206.75 | 0.99933
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-01-01 | Overhead | 244368.41 | 251106.4 | 241341.96 | 246410.19 | 6737.99 | 2.757% | -9764.44 | 0.96111
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-01-01 | Travel | 56834.63 | 58009.33 | 56199.79 | 57270.21 | 1174.7 | 2.067% | -1809.54 | 0.96881
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-01-01 | Other Direct Costs | 87587.19 | 88127.11 | 86907.51 | 87716.56 | 539.92 | 0.6164% | -1219.6 | 0.98616
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-02-01 | Labor | 540976.45 | 539386.9 | 547734.56 | 534299.28 | -1589.55 | -0.2938% | 8347.66 | 1.0155
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-02-01 | Materials | 436083.8 | 428932.47 | 445937.03 | 432316.77 | -7151.33 | -1.64% | 17004.56 | 1.0396
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-02-01 | Subcontracts | 322065.91 | 323867.57 | 317414.69 | 321109.44 | 1801.66 | 0.5594% | -6452.88 | 0.98008
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-02-01 | Overhead | 234582.26 | 241817.97 | 236441.18 | 242526.63 | 7235.71 | 3.085% | -5376.79 | 0.97777
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-02-01 | Travel | 56103.54 | 54432.49 | 55874.11 | 54648.34 | -1671.05 | -2.979% | 1441.62 | 1.0265
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-02-01 | Other Direct Costs | 92182.95 | 91655.98 | 93714.1 | 92759.11 | -526.97 | -0.5717% | 2058.12 | 1.0225
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-03-01 | Labor | 541634.81 | 547664.19 | 551922.49 | 553069.6 | 6029.38 | 1.113% | 4258.3 | 1.0078
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-03-01 | Materials | 414974.38 | 412531.64 | 404414.59 | 420842.37 | -2442.74 | -0.5886% | -8117.05 | 0.98032
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-03-01 | Subcontracts | 349103.41 | 342729.88 | 353519.96 | 344151.17 | -6373.53 | -1.826% | 10790.08 | 1.0315
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-03-01 | Overhead | 249726.78 | 252934.68 | 252705.28 | 253076.02 | 3207.9 | 1.285% | -229.4 | 0.99909
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-03-01 | Travel | 57070.74 | 55498.94 | 57322.08 | 56467.73 | -1571.8 | -2.754% | 1823.14 | 1.0328
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-03-01 | Other Direct Costs | 89070.33 | 90697.55 | 90541.52 | 90959.5 | 1627.22 | 1.827% | -156.03 | 0.99828
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-04-01 | Labor | 536079.13 | 543774.75 | 537072.78 | 539159.21 | 7695.62 | 1.436% | -6701.97 | 0.98768
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-04-01 | Materials | 443775.09 | 455736.18 | 445963.5 | 453012.87 | 11961.09 | 2.695% | -9772.68 | 0.97856
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-04-01 | Subcontracts | 352404.59 | 341392.01 | 342172.76 | 341138.72 | -11012.58 | -3.125% | 780.75 | 1.0023
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-04-01 | Overhead | 243780.93 | 237654.32 | 238305.66 | 239133.1 | -6126.61 | -2.513% | 651.34 | 1.0027
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-04-01 | Travel | 58865.88 | 60894.4 | 59753 | 59527.58 | 2028.52 | 3.446% | -1141.4 | 0.98126
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-04-01 | Other Direct Costs | 92613.74 | 95383.86 | 93407.69 | 95331.31 | 2770.12 | 2.991% | -1976.17 | 0.97928
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-05-01 | Labor | 544526.98 | 529689.99 | 540837.26 | 531518.99 | -14836.99 | -2.725% | 11147.27 | 1.021
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-05-01 | Materials | 445161.96 | 440475.01 | 449318.2 | 444299.81 | -4686.95 | -1.053% | 8843.19 | 1.0201
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-05-01 | Subcontracts | 343445.58 | 353032.97 | 348940.13 | 348297.15 | 9587.39 | 2.792% | -4092.84 | 0.98841
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-05-01 | Overhead | 246995.13 | 241454.48 | 251331.73 | 241520.39 | -5540.65 | -2.243% | 9877.25 | 1.0409
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-05-01 | Travel | 59796.89 | 61307.4 | 58670.06 | 60940.33 | 1510.51 | 2.526% | -2637.34 | 0.95698
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-05-01 | Other Direct Costs | 95746.57 | 95157.03 | 98237.85 | 96700.25 | -589.54 | -0.6157% | 3080.82 | 1.0324
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-06-01 | Labor | 550681.67 | 565165.19 | 542711.49 | 555764.91 | 14483.52 | 2.63% | -22453.7 | 0.96027
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-06-01 | Materials | 423369.92 | 432290.79 | 434337.64 | 436458.58 | 8920.87 | 2.107% | 2046.85 | 1.0047
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-06-01 | Subcontracts | 347005.69 | 336423.87 | 337968.58 | 339122.09 | -10581.82 | -3.049% | 1544.71 | 1.0046
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-06-01 | Overhead | 246562.55 | 254852.97 | 252370.56 | 256179.89 | 8290.42 | 3.362% | -2482.41 | 0.99026
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-06-01 | Travel | 59481.21 | 57667.49 | 60351.6 | 58945.86 | -1813.72 | -3.049% | 2684.11 | 1.0465
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-06-01 | Other Direct Costs | 93032.06 | 93669.13 | 93618.67 | 93910.34 | 637.07 | 0.6848% | -50.46 | 0.99946
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-07-01 | Labor | 554769.17 | 555323.05 | 557405.96 | 556289.04 | 553.88 | 0.09984% | 2082.91 | 1.0038
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-07-01 | Materials | 442702.02 | 428809.81 | 449576.39 | 434022.14 | -13892.21 | -3.138% | 20766.58 | 1.0484
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-07-01 | Subcontracts | 363247.35 | 359918.01 | 363427.69 | 366676.26 | -3329.34 | -0.9165% | 3509.68 | 1.0098
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-07-01 | Overhead | 251991.43 | 244367.34 | 245401.15 | 248138.35 | -7624.09 | -3.026% | 1033.81 | 1.0042
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-07-01 | Travel | 58547.91 | 57372.36 | 58563.54 | 58552.43 | -1175.55 | -2.008% | 1191.18 | 1.0208
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-07-01 | Other Direct Costs | 92961.62 | 91833.08 | 90215.13 | 93310.58 | -1128.54 | -1.214% | -1617.95 | 0.98238
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-08-01 | Labor | 561108.54 | 548742.11 | 565559.65 | 556254.93 | -12366.43 | -2.204% | 16817.54 | 1.0306
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-08-01 | Materials | 434466.36 | 429443.86 | 432732.63 | 432917.45 | -5022.5 | -1.156% | 3288.77 | 1.0077
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-08-01 | Subcontracts | 339324.12 | 338624.32 | 332891.82 | 336601.89 | -699.8 | -0.2062% | -5732.5 | 0.98307
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-08-01 | Overhead | 260521.28 | 256118.02 | 257127.68 | 255379.99 | -4403.26 | -1.69% | 1009.66 | 1.0039
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-08-01 | Travel | 63329.47 | 61541.52 | 62327.38 | 62422.5 | -1787.95 | -2.823% | 785.86 | 1.0128
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-08-01 | Other Direct Costs | 93617.77 | 95012.68 | 95028.55 | 95759.59 | 1394.91 | 1.49% | 15.87 | 1.0002
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-09-01 | Labor | 561755.38 | 577769.04 | 576832.58 | 572539.56 | 16013.66 | 2.851% | -936.46 | 0.99838
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-09-01 | Materials | 435225.07 | 445765.52 | 442207.65 | 449599.48 | 10540.45 | 2.422% | -3557.87 | 0.99202
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-09-01 | Subcontracts | 366368.55 | 375728.28 | 377103.8 | 371757.72 | 9359.73 | 2.555% | 1375.52 | 1.0037
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-09-01 | Overhead | 264636.3 | 270240.68 | 269584.48 | 269955.49 | 5604.38 | 2.118% | -656.2 | 0.99757
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-09-01 | Travel | 59545.39 | 59517.81 | 60074.16 | 59084.03 | -27.58 | -0.04632% | 556.35 | 1.0093
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-09-01 | Other Direct Costs | 92626.09 | 90202.81 | 94485.26 | 92076.96 | -2423.28 | -2.616% | 4282.45 | 1.0475
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-10-01 | Labor | 567903.23 | 558987.95 | 574942.68 | 565142.85 | -8915.28 | -1.57% | 15954.73 | 1.0285
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-10-01 | Materials | 456169.25 | 464144.71 | 461182.17 | 468547.95 | 7975.46 | 1.748% | -2962.54 | 0.99362
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-10-01 | Subcontracts | 349198.19 | 338174.48 | 341429.3 | 341333.38 | -11023.71 | -3.157% | 3254.82 | 1.0096
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-10-01 | Overhead | 272366.03 | 265153.66 | 265445.63 | 267815.61 | -7212.37 | -2.648% | 291.97 | 1.0011
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-10-01 | Travel | 62434.09 | 63386.04 | 64073.82 | 63508.77 | 951.95 | 1.525% | 687.78 | 1.0109
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-10-01 | Other Direct Costs | 98502.17 | 95728.42 | 97620.49 | 96369.55 | -2773.75 | -2.816% | 1892.07 | 1.0198
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-11-01 | Labor | 568195.78 | 579726.54 | 561793.7 | 573394.22 | 11530.76 | 2.029% | -17932.84 | 0.96907
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-11-01 | Materials | 447390.72 | 432375.67 | 446570.68 | 442588.33 | -15015.05 | -3.356% | 14195.01 | 1.0328
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-11-01 | Subcontracts | 375388.43 | 379570.48 | 377965.63 | 380177.54 | 4182.05 | 1.114% | -1604.85 | 0.99577
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-11-01 | Overhead | 267472.78 | 272879.75 | 274471.05 | 274246.13 | 5406.97 | 2.022% | 1591.3 | 1.0058
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-11-01 | Travel | 64773.21 | 64716.29 | 66660.43 | 64346.91 | -56.92 | -0.08788% | 1944.14 | 1.03
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-11-01 | Other Direct Costs | 94067.05 | 90974.65 | 91714.61 | 91618.22 | -3092.4 | -3.287% | 739.96 | 1.0081
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-12-01 | Labor | 575484.46 | 581911.72 | 560994.47 | 589303.31 | 6427.26 | 1.117% | -20917.25 | 0.96405
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-12-01 | Materials | 459916.49 | 454961.56 | 468529.08 | 451878.23 | -4954.93 | -1.077% | 13567.52 | 1.0298
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-12-01 | Subcontracts | 371539.13 | 361988.23 | 364745.23 | 367204.25 | -9550.9 | -2.571% | 2757 | 1.0076
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-12-01 | Overhead | 274235.16 | 277680.63 | 271068.35 | 275513.65 | 3445.47 | 1.256% | -6612.28 | 0.97619
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-12-01 | Travel | 64105.54 | 62791.56 | 64588.11 | 62659.41 | -1313.98 | -2.05% | 1796.55 | 1.0286
AP-101 | Falcon | DoD | Aircraft | Sarah Chen | 2025-12-01 | Other Direct Costs | 96946.98 | 98317.79 | 94773.36 | 98191.6 | 1370.81 | 1.414% | -3544.43 | 0.96395
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-01-01 | Labor | 421163.12 | 435412.66 | 415164.24 | 425882.85 | 14249.54 | 3.383% | -20248.42 | 0.9535
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-01-01 | Materials | 333455.95 | 330242.63 | 334033.37 | 332206.78 | -3213.32 | -0.9636% | 3790.74 | 1.0115
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-01-01 | Subcontracts | 273937.03 | 274156.91 | 276882.63 | 277845.86 | 219.88 | 0.08027% | 2725.72 | 1.0099
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-01-01 | Overhead | 192653.52 | 190677.41 | 191032.02 | 190763.8 | -1976.11 | -1.026% | 354.61 | 1.0019
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-01-01 | Travel | 47241.89 | 48585.53 | 47354.62 | 47792.26 | 1343.64 | 2.844% | -1230.91 | 0.97467
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-01-01 | Other Direct Costs | 71403.61 | 70616.86 | 72090.34 | 71635.96 | -786.75 | -1.102% | 1473.48 | 1.0209
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-02-01 | Labor | 442418.42 | 439705.53 | 448227.94 | 446424.56 | -2712.89 | -0.6132% | 8522.41 | 1.0194
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-02-01 | Materials | 336413.32 | 347625.88 | 338565.52 | 339706.39 | 11212.56 | 3.333% | -9060.36 | 0.97394
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-02-01 | Subcontracts | 263165.3 | 266954.73 | 262230.27 | 267174.44 | 3789.43 | 1.44% | -4724.46 | 0.9823
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-02-01 | Overhead | 197213.64 | 195932.43 | 193810.65 | 194330.66 | -1281.21 | -0.6497% | -2121.78 | 0.98917
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-02-01 | Travel | 47591.67 | 46072.68 | 47690.01 | 46723.36 | -1518.99 | -3.192% | 1617.33 | 1.0351
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-02-01 | Other Direct Costs | 69577.81 | 69933.99 | 71332.95 | 69408.58 | 356.18 | 0.5119% | 1398.96 | 1.02
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-03-01 | Labor | 422483.09 | 415601.08 | 422758.18 | 415781.7 | -6882.01 | -1.629% | 7157.1 | 1.0172
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-03-01 | Materials | 348291.33 | 342420.56 | 338845.3 | 349027.1 | -5870.77 | -1.686% | -3575.26 | 0.98956
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-03-01 | Subcontracts | 266403.94 | 266915.06 | 261636.93 | 270962.66 | 511.12 | 0.1919% | -5278.13 | 0.98023
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-03-01 | Overhead | 201930.54 | 207486.81 | 207858.99 | 206760.46 | 5556.27 | 2.752% | 372.18 | 1.0018
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-03-01 | Travel | 47259.3 | 47554.68 | 46553.66 | 47584.23 | 295.38 | 0.625% | -1001.02 | 0.97895
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-03-01 | Other Direct Costs | 72337.38 | 71095.84 | 71817.42 | 72288.5 | -1241.54 | -1.716% | 721.58 | 1.0101
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-04-01 | Labor | 448622.79 | 464062.93 | 444507.9 | 458208.87 | 15440.14 | 3.442% | -19555.03 | 0.95786
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-04-01 | Materials | 353598.5 | 354045.13 | 345238.77 | 358970.34 | 446.63 | 0.1263% | -8806.36 | 0.97513
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-04-01 | Subcontracts | 269338.89 | 263697.39 | 269465.27 | 268285.54 | -5641.5 | -2.095% | 5767.88 | 1.0219
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-04-01 | Overhead | 192716.01 | 191666.51 | 195710.78 | 193997.07 | -1049.5 | -0.5446% | 4044.27 | 1.0211
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-04-01 | Travel | 46667.53 | 45770.56 | 46725.72 | 46409.59 | -896.97 | -1.922% | 955.16 | 1.0209
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-04-01 | Other Direct Costs | 73894.34 | 76378.16 | 71735.34 | 76123.2 | 2483.82 | 3.361% | -4642.82 | 0.93921
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-05-01 | Labor | 434177.8 | 447201.7 | 441010.73 | 448297.69 | 13023.9 | 3% | -6190.97 | 0.98616
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-05-01 | Materials | 344011.69 | 335119.48 | 338524.69 | 338213.66 | -8892.21 | -2.585% | 3405.21 | 1.0102
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-05-01 | Subcontracts | 279033.58 | 273366.57 | 283327.5 | 272768.92 | -5667.01 | -2.031% | 9960.93 | 1.0364
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-05-01 | Overhead | 206845.29 | 201936.8 | 202505.37 | 201613.34 | -4908.49 | -2.373% | 568.57 | 1.0028
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-05-01 | Travel | 46865.02 | 48081.12 | 45469.56 | 47543.06 | 1216.1 | 2.595% | -2611.56 | 0.94568
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-05-01 | Other Direct Costs | 74904.96 | 75592.23 | 75343.04 | 74654.13 | 687.27 | 0.9175% | -249.19 | 0.9967
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-06-01 | Labor | 453478.5 | 450461.35 | 452587.91 | 452941.81 | -3017.15 | -0.6653% | 2126.56 | 1.0047
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-06-01 | Materials | 342599.33 | 334585.03 | 332581.96 | 337503.13 | -8014.3 | -2.339% | -2003.07 | 0.99401
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-06-01 | Subcontracts | 276522.96 | 285257.43 | 281662.15 | 280408.91 | 8734.47 | 3.159% | -3595.28 | 0.9874
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-06-01 | Overhead | 195315.81 | 194861.7 | 196692.53 | 196347.34 | -454.11 | -0.2325% | 1830.83 | 1.0094
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-06-01 | Travel | 46362.04 | 46646.73 | 46918.33 | 46896.4 | 284.69 | 0.6141% | 271.6 | 1.0058
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-06-01 | Other Direct Costs | 75941.58 | 75203.98 | 75608.21 | 75082.96 | -737.6 | -0.9713% | 404.23 | 1.0054
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-07-01 | Labor | 447792.97 | 445743.69 | 456942.89 | 451283.52 | -2049.28 | -0.4576% | 11199.2 | 1.0251
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-07-01 | Materials | 344425.5 | 347698.34 | 341513.02 | 351032.06 | 3272.84 | 0.9502% | -6185.32 | 0.98221
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-07-01 | Subcontracts | 289658.35 | 299477.37 | 288759.09 | 297761.11 | 9819.02 | 3.39% | -10718.28 | 0.96421
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-07-01 | Overhead | 201642.53 | 206965.13 | 204414.06 | 208061.59 | 5322.6 | 2.64% | -2551.07 | 0.98767
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-07-01 | Travel | 48271.82 | 48888.23 | 47621.99 | 49171.09 | 616.41 | 1.277% | -1266.24 | 0.9741
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-07-01 | Other Direct Costs | 73526.59 | 75519.75 | 72555.12 | 75917.63 | 1993.16 | 2.711% | -2964.63 | 0.96074
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-08-01 | Labor | 443963.02 | 483236.15 | 438861.61 | 468049.48 | 39273.13 | 8.846% | -44374.54 | 0.90817
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-08-01 | Materials | 349566.66 | 349179.66 | 354327.95 | 346211.4 | -387 | -0.1107% | 5148.29 | 1.0147
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-08-01 | Subcontracts | 289928.97 | 298029.95 | 284762.15 | 292431.06 | 8100.98 | 2.794% | -13267.8 | 0.95548
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-08-01 | Overhead | 204802.95 | 202004.48 | 207058.03 | 201260.48 | -2798.47 | -1.366% | 5053.55 | 1.025
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-08-01 | Travel | 48615.5 | 49228.63 | 47908.29 | 49882.42 | 613.13 | 1.261% | -1320.34 | 0.97318
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-08-01 | Other Direct Costs | 76689.2 | 76775.65 | 75721.38 | 76553.14 | 86.45 | 0.1127% | -1054.27 | 0.98627
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-09-01 | Labor | 446756.23 | 491925.76 | 434113.46 | 477637.41 | 45169.53 | 10.11% | -57812.3 | 0.88248
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-09-01 | Materials | 353168.45 | 350375.18 | 345311.08 | 347940 | -2793.27 | -0.7909% | -5064.1 | 0.98555
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-09-01 | Subcontracts | 289469.58 | 283199.1 | 293586.6 | 289805.89 | -6270.48 | -2.166% | 10387.5 | 1.0367
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-09-01 | Overhead | 207380.67 | 210541.11 | 210293.15 | 208353.91 | 3160.44 | 1.524% | -247.96 | 0.99882
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-09-01 | Travel | 50249.59 | 51874.69 | 49851.72 | 51680.44 | 1625.1 | 3.234% | -2022.97 | 0.961
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-09-01 | Other Direct Costs | 74395.16 | 72183.04 | 74419.58 | 72120.02 | -2212.12 | -2.973% | 2236.54 | 1.031
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-10-01 | Labor | 455585.62 | 483275.02 | 444217.81 | 470386.19 | 27689.4 | 6.078% | -39057.21 | 0.91918
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-10-01 | Materials | 363025.47 | 355107.51 | 371544.83 | 361409.51 | -7917.96 | -2.181% | 16437.32 | 1.0463
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-10-01 | Subcontracts | 282398.54 | 290386.04 | 286402.2 | 288405.69 | 7987.5 | 2.828% | -3983.84 | 0.98628
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-10-01 | Overhead | 212592.5 | 212818.77 | 217558.96 | 211987.4 | 226.27 | 0.1064% | 4740.19 | 1.0223
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-10-01 | Travel | 50095.54 | 49550.03 | 49175.9 | 49177.18 | -545.51 | -1.089% | -374.13 | 0.99245
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-10-01 | Other Direct Costs | 79665.42 | 79934.3 | 80455.03 | 80836.62 | 268.88 | 0.3375% | 520.73 | 1.0065
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-11-01 | Labor | 485153.12 | 515989.51 | 482940.28 | 505080.82 | 30836.39 | 6.356% | -33049.23 | 0.93595
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-11-01 | Materials | 375969.91 | 382809.85 | 381200.53 | 382270.16 | 6839.94 | 1.819% | -1609.32 | 0.9958
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-11-01 | Subcontracts | 293229.69 | 290798.13 | 289506.17 | 293012.66 | -2431.56 | -0.8292% | -1291.96 | 0.99556
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-11-01 | Overhead | 210726.03 | 216128.66 | 212713.97 | 214021.58 | 5402.63 | 2.564% | -3414.69 | 0.9842
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-11-01 | Travel | 49786.94 | 49448.58 | 49105.4 | 49853.45 | -338.36 | -0.6796% | -343.18 | 0.99306
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-11-01 | Other Direct Costs | 78179.04 | 80681.53 | 78003.25 | 80602.17 | 2502.49 | 3.201% | -2678.28 | 0.9668
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-12-01 | Labor | 488990.12 | 516326.82 | 486721.68 | 515338.63 | 27336.7 | 5.59% | -29605.14 | 0.94266
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-12-01 | Materials | 383145.27 | 380878.26 | 381824.05 | 383613.67 | -2267.01 | -0.5917% | 945.79 | 1.0025
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-12-01 | Subcontracts | 299670.77 | 299661.19 | 297965.14 | 303321.7 | -9.58 | -0.003197% | -1696.05 | 0.99434
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-12-01 | Overhead | 221386.9 | 216208.6 | 226883.64 | 220830.06 | -5178.3 | -2.339% | 10675.04 | 1.0494
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-12-01 | Travel | 52085.84 | 51458.63 | 53015.36 | 52061.42 | -627.21 | -1.204% | 1556.73 | 1.0303
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2024-12-01 | Other Direct Costs | 75977.98 | 78523.87 | 78052.85 | 78749.61 | 2545.89 | 3.351% | -471.02 | 0.994
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-01-01 | Labor | 435012.11 | 468511.89 | 429297.76 | 464351.05 | 33499.78 | 7.701% | -39214.13 | 0.9163
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-01-01 | Materials | 344687.28 | 355402.06 | 348745.67 | 352023.25 | 10714.78 | 3.109% | -6656.39 | 0.98127
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-01-01 | Subcontracts | 281896.73 | 285670.07 | 284262.03 | 285571.75 | 3773.34 | 1.339% | -1408.04 | 0.99507
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-01-01 | Overhead | 206921.21 | 209979.85 | 206395.7 | 211849.16 | 3058.64 | 1.478% | -3584.15 | 0.98293
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-01-01 | Travel | 47748.99 | 47515.9 | 46630.88 | 48146.69 | -233.09 | -0.4882% | -885.02 | 0.98137
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-01-01 | Other Direct Costs | 73377.17 | 71981.66 | 71512.97 | 71652.07 | -1395.51 | -1.902% | -468.69 | 0.99349
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-02-01 | Labor | 461983.93 | 506204 | 450047.43 | 491677.69 | 44220.07 | 9.572% | -56156.57 | 0.88906
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-02-01 | Materials | 365271.08 | 357155.53 | 369419.02 | 356691.67 | -8115.55 | -2.222% | 12263.49 | 1.0343
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-02-01 | Subcontracts | 288722.61 | 285105.22 | 291253.31 | 288214.14 | -3617.39 | -1.253% | 6148.09 | 1.0216
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-02-01 | Overhead | 209163.97 | 203404.72 | 204540.45 | 208969.12 | -5759.25 | -2.753% | 1135.73 | 1.0056
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-02-01 | Travel | 50184.3 | 51305.94 | 49031.91 | 50361.79 | 1121.64 | 2.235% | -2274.03 | 0.95568
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-02-01 | Other Direct Costs | 76689.15 | 76953.17 | 76779.36 | 76749.68 | 264.02 | 0.3443% | -173.81 | 0.99774
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-03-01 | Labor | 468011.68 | 505697.53 | 472236.35 | 496818.09 | 37685.85 | 8.052% | -33461.18 | 0.93383
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-03-01 | Materials | 345549.68 | 340523.72 | 351405.71 | 343464.42 | -5025.96 | -1.454% | 10881.99 | 1.032
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-03-01 | Subcontracts | 277901.17 | 268807.9 | 280951.16 | 275972.47 | -9093.27 | -3.272% | 12143.26 | 1.0452
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-03-01 | Overhead | 202060.09 | 204821.7 | 206612.24 | 204313.59 | 2761.61 | 1.367% | 1790.54 | 1.0087
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-03-01 | Travel | 47421.19 | 48567.59 | 46854.51 | 48916.61 | 1146.4 | 2.417% | -1713.08 | 0.96473
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-03-01 | Other Direct Costs | 78458.86 | 80177.76 | 78438.05 | 78663.95 | 1718.9 | 2.191% | -1739.71 | 0.9783
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-04-01 | Labor | 479609.41 | 527196.93 | 480151.05 | 516884.2 | 47587.52 | 9.922% | -47045.88 | 0.91076
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-04-01 | Materials | 358828.92 | 347248.73 | 364529 | 350918.78 | -11580.19 | -3.227% | 17280.27 | 1.0498
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-04-01 | Subcontracts | 294442.59 | 302549.33 | 301078.56 | 300038.49 | 8106.74 | 2.753% | -1470.77 | 0.99514
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-04-01 | Overhead | 209511.33 | 215541.42 | 215017.82 | 210989.14 | 6030.09 | 2.878% | -523.6 | 0.99757
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-04-01 | Travel | 50692.71 | 49094.84 | 50275.97 | 49735.57 | -1597.87 | -3.152% | 1181.13 | 1.0241
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-04-01 | Other Direct Costs | 77250.98 | 78329.4 | 78118.33 | 78546.32 | 1078.42 | 1.396% | -211.07 | 0.99731
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-05-01 | Labor | 455786.62 | 496548.18 | 463864.79 | 476858.75 | 40761.56 | 8.943% | -32683.39 | 0.93418
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-05-01 | Materials | 373064.58 | 379532.29 | 375759.73 | 383175.8 | 6467.71 | 1.734% | -3772.56 | 0.99006
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-05-01 | Subcontracts | 281593.88 | 289279.75 | 288097.93 | 289594.29 | 7685.87 | 2.729% | -1181.82 | 0.99591
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-05-01 | Overhead | 207963.73 | 215116.66 | 209080.11 | 214715.53 | 7152.93 | 3.44% | -6036.55 | 0.97194
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-05-01 | Travel | 48848.39 | 48736.53 | 49344.65 | 49383.67 | -111.86 | -0.229% | 608.12 | 1.0125
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-05-01 | Other Direct Costs | 78742.51 | 81105.87 | 80168.76 | 79503.39 | 2363.36 | 3.001% | -937.11 | 0.98845
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-06-01 | Labor | 479265.99 | 535655.9 | 477530.39 | 510971.72 | 56389.91 | 11.77% | -58125.51 | 0.89149
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-06-01 | Materials | 382899.58 | 377267.16 | 379563.12 | 376786.64 | -5632.42 | -1.471% | 2295.96 | 1.0061
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-06-01 | Subcontracts | 294687.95 | 296734.02 | 289852.81 | 299192.13 | 2046.07 | 0.6943% | -6881.21 | 0.97681
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-06-01 | Overhead | 217459.09 | 218801.48 | 221025.37 | 221537 | 1342.39 | 0.6173% | 2223.89 | 1.0102
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-06-01 | Travel | 49196.59 | 50651.8 | 47896.87 | 49875.46 | 1455.21 | 2.958% | -2754.93 | 0.94561
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-06-01 | Other Direct Costs | 75467.89 | 74773.56 | 76229.12 | 74909.06 | -694.33 | -0.92% | 1455.56 | 1.0195
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-07-01 | Labor | 456646.32 | 510914.1 | 443326.16 | 497608.89 | 54267.78 | 11.88% | -67587.94 | 0.86771
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-07-01 | Materials | 357638.95 | 369618.78 | 356459.79 | 367539.7 | 11979.83 | 3.35% | -13158.99 | 0.9644
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-07-01 | Subcontracts | 296454.28 | 291696.01 | 295936.07 | 298503.79 | -4758.27 | -1.605% | 4240.06 | 1.0145
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-07-01 | Overhead | 219334.73 | 216977.51 | 215092.01 | 215974.71 | -2357.22 | -1.075% | -1885.5 | 0.99131
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-07-01 | Travel | 52661.11 | 52057.61 | 51782.72 | 52298.3 | -603.5 | -1.146% | -274.89 | 0.99472
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-07-01 | Other Direct Costs | 81580.33 | 80282.69 | 83953.85 | 80439.72 | -1297.64 | -1.591% | 3671.16 | 1.0457
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-08-01 | Labor | 463345.3 | 535847.99 | 466936.87 | 506977.07 | 72502.69 | 15.65% | -68911.12 | 0.8714
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-08-01 | Materials | 375332.79 | 373774.39 | 385603.23 | 373923.15 | -1558.4 | -0.4152% | 11828.84 | 1.0316
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-08-01 | Subcontracts | 294641.35 | 295903.13 | 293095.31 | 299960.17 | 1261.78 | 0.4282% | -2807.82 | 0.99051
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-08-01 | Overhead | 213632.63 | 215520.14 | 207450.05 | 214667.72 | 1887.51 | 0.8835% | -8070.09 | 0.96256
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-08-01 | Travel | 51783.16 | 51623.21 | 52153.96 | 52333.52 | -159.95 | -0.3089% | 530.75 | 1.0103
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-08-01 | Other Direct Costs | 78491.15 | 79174.28 | 78384.84 | 80298.54 | 683.13 | 0.8703% | -789.44 | 0.99003
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-09-01 | Labor | 480725.94 | 531706.59 | 487565.14 | 516837.8 | 50980.65 | 10.6% | -44141.45 | 0.91698
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-09-01 | Materials | 394319.06 | 385357.38 | 393876.14 | 394122.74 | -8961.68 | -2.273% | 8518.76 | 1.0221
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-09-01 | Subcontracts | 309093.27 | 314011.21 | 300398.53 | 314418.68 | 4917.94 | 1.591% | -13612.68 | 0.95665
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-09-01 | Overhead | 214569.36 | 214207.59 | 216913.93 | 213700.23 | -361.77 | -0.1686% | 2706.34 | 1.0126
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-09-01 | Travel | 53269.52 | 54559.65 | 52124.07 | 54927.1 | 1290.13 | 2.422% | -2435.58 | 0.95536
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-09-01 | Other Direct Costs | 82671.88 | 84872.61 | 82023.41 | 84896.59 | 2200.73 | 2.662% | -2849.2 | 0.96643
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-10-01 | Labor | 478842.96 | 543335.09 | 465739.12 | 526195.3 | 64492.13 | 13.47% | -77595.97 | 0.85719
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-10-01 | Materials | 368312.22 | 374175.81 | 363653.19 | 373806.82 | 5863.59 | 1.592% | -10522.62 | 0.97188
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-10-01 | Subcontracts | 301735.43 | 305222.64 | 297545.63 | 302662.35 | 3487.21 | 1.156% | -7677.01 | 0.97485
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-10-01 | Overhead | 225532.54 | 223817.86 | 222153.13 | 228397.04 | -1714.68 | -0.7603% | -1664.73 | 0.99256
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-10-01 | Travel | 53028.92 | 53231.08 | 52855.56 | 53123.98 | 202.16 | 0.3812% | -375.52 | 0.99295
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-10-01 | Other Direct Costs | 78047.43 | 75957.84 | 79032.84 | 77950.29 | -2089.59 | -2.677% | 3075 | 1.0405
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-11-01 | Labor | 501870.79 | 575713.68 | 491659.8 | 558154.41 | 73842.89 | 14.71% | -84053.88 | 0.854
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-11-01 | Materials | 373074.32 | 377020.88 | 381872.92 | 378997.47 | 3946.56 | 1.058% | 4852.04 | 1.0129
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-11-01 | Subcontracts | 309912.03 | 317919.01 | 306592.95 | 317209.24 | 8006.98 | 2.584% | -11326.06 | 0.96437
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-11-01 | Overhead | 227432.64 | 220169.42 | 226816.36 | 224081 | -7263.22 | -3.194% | 6646.94 | 1.0302
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-11-01 | Travel | 52580.33 | 51500.62 | 51796.19 | 51918.35 | -1079.71 | -2.053% | 295.57 | 1.0057
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-11-01 | Other Direct Costs | 79813.78 | 80404.68 | 79135.14 | 80858.93 | 590.9 | 0.7403% | -1269.54 | 0.98421
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-12-01 | Labor | 482497.75 | 553368.69 | 481354.63 | 533951.04 | 70870.94 | 14.69% | -72014.06 | 0.86986
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-12-01 | Materials | 390304.35 | 393502.59 | 390349.62 | 391225.93 | 3198.24 | 0.8194% | -3152.97 | 0.99199
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-12-01 | Subcontracts | 294837.65 | 291107.63 | 301883.28 | 296749.39 | -3730.02 | -1.265% | 10775.65 | 1.037
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-12-01 | Overhead | 226318.11 | 231510.18 | 221802.43 | 232805.79 | 5192.07 | 2.294% | -9707.75 | 0.95807
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-12-01 | Travel | 54602.13 | 52788.27 | 56047.13 | 54369.09 | -1813.86 | -3.322% | 3258.86 | 1.0617
AP-102 | Sentinel | DoD | Missile Systems | Marcus Reed | 2025-12-01 | Other Direct Costs | 83341.43 | 81536.32 | 85477.4 | 83512.32 | -1805.11 | -2.166% | 3941.08 | 1.0483
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-01-01 | Labor | 568351.89 | 582072.51 | 560420.37 | 579527.55 | 13720.62 | 2.414% | -21652.14 | 0.9628
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-01-01 | Materials | 438938.32 | 439062.95 | 443939.2 | 444583.67 | 124.63 | 0.02839% | 4876.25 | 1.0111
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-01-01 | Subcontracts | 350064.62 | 361112.19 | 355070.6 | 360866.14 | 11047.57 | 3.156% | -6041.59 | 0.98327
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-01-01 | Overhead | 242654.28 | 250377.88 | 237170.02 | 247843.9 | 7723.6 | 3.183% | -13207.86 | 0.94725
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-01-01 | Travel | 61163.88 | 61678.73 | 60145.44 | 61655.01 | 514.85 | 0.8418% | -1533.29 | 0.97514
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-01-01 | Other Direct Costs | 93900.93 | 90825.87 | 91864.2 | 91598.18 | -3075.06 | -3.275% | 1038.33 | 1.0114
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-02-01 | Labor | 576381.12 | 591077.27 | 562050.82 | 594977.21 | 14696.15 | 2.55% | -29026.45 | 0.95089
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-02-01 | Materials | 452819.88 | 459302.24 | 455571.25 | 463124.76 | 6482.36 | 1.432% | -3730.99 | 0.99188
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-02-01 | Subcontracts | 342384.9 | 337017.81 | 335806.27 | 343142.43 | -5367.09 | -1.568% | -1211.54 | 0.99641
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-02-01 | Overhead | 245342.37 | 236908.01 | 242752.96 | 237296.46 | -8434.36 | -3.438% | 5844.95 | 1.0247
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-02-01 | Travel | 59308.94 | 59892.27 | 60133.18 | 60632.58 | 583.33 | 0.9835% | 240.91 | 1.004
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-02-01 | Other Direct Costs | 89472.67 | 91329.97 | 92147.1 | 91351.52 | 1857.3 | 2.076% | 817.13 | 1.0089
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-03-01 | Labor | 545486.33 | 558978.13 | 546996.34 | 549881.81 | 13491.8 | 2.473% | -11981.79 | 0.97856
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-03-01 | Materials | 440455.33 | 455400.46 | 431679.58 | 449242.93 | 14945.13 | 3.393% | -23720.88 | 0.94791
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-03-01 | Subcontracts | 356469.37 | 355930.48 | 351801.04 | 356511.63 | -538.89 | -0.1512% | -4129.44 | 0.9884
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-03-01 | Overhead | 248585.14 | 248899.82 | 244457.53 | 252988.73 | 314.68 | 0.1266% | -4442.29 | 0.98215
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-03-01 | Travel | 58332.87 | 56912.14 | 57848.6 | 57516.79 | -1420.73 | -2.436% | 936.46 | 1.0165
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-03-01 | Other Direct Costs | 90671.49 | 90791.69 | 89235.86 | 92243.55 | 120.2 | 0.1326% | -1555.83 | 0.98286
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-04-01 | Labor | 572609.06 | 570619.92 | 562260.2 | 581415.63 | -1989.14 | -0.3474% | -8359.72 | 0.98535
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-04-01 | Materials | 445387.46 | 451730.25 | 446534.21 | 453900.83 | 6342.79 | 1.424% | -5196.04 | 0.9885
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-04-01 | Subcontracts | 356783.89 | 364955.43 | 364043.04 | 365443.13 | 8171.54 | 2.29% | -912.39 | 0.9975
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-04-01 | Overhead | 263981.31 | 257421.08 | 261608.59 | 264243.85 | -6560.23 | -2.485% | 4187.51 | 1.0163
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-04-01 | Travel | 62560.38 | 63569.12 | 63146.77 | 63312.09 | 1008.74 | 1.612% | -422.35 | 0.99336
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-04-01 | Other Direct Costs | 94131.12 | 97012.34 | 94332.37 | 97190.5 | 2881.22 | 3.061% | -2679.97 | 0.97237
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-05-01 | Labor | 565139 | 579445.27 | 564354.19 | 577945.75 | 14306.27 | 2.531% | -15091.08 | 0.97396
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-05-01 | Materials | 450761.23 | 435206.5 | 449715.65 | 438061.62 | -15554.73 | -3.451% | 14509.15 | 1.0333
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-05-01 | Subcontracts | 362363.54 | 371636.48 | 358564.48 | 367356.47 | 9272.94 | 2.559% | -13072 | 0.96483
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-05-01 | Overhead | 248847.26 | 253287.27 | 253080.3 | 255421.52 | 4440.01 | 1.784% | -206.97 | 0.99918
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-05-01 | Travel | 61870.5 | 59916.33 | 63664.37 | 61131.56 | -1954.17 | -3.158% | 3748.04 | 1.0626
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-05-01 | Other Direct Costs | 91715.36 | 93347.89 | 93604.12 | 92998.03 | 1632.53 | 1.78% | 256.23 | 1.0027
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-06-01 | Labor | 555470.68 | 557455.25 | 571136.42 | 561476.07 | 1984.57 | 0.3573% | 13681.17 | 1.0245
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-06-01 | Materials | 438062.3 | 493943.99 | 426317.43 | 472777.49 | 55881.69 | 12.76% | -67626.56 | 0.86309
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-06-01 | Subcontracts | 369225.74 | 377688.94 | 379576.38 | 379632.66 | 8463.2 | 2.292% | 1887.44 | 1.005
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-06-01 | Overhead | 257341.2 | 265189.04 | 251343.85 | 264004.49 | 7847.84 | 3.05% | -13845.19 | 0.94779
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-06-01 | Travel | 60278.34 | 60245.13 | 61119.1 | 59946.76 | -33.21 | -0.05509% | 873.97 | 1.0145
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-06-01 | Other Direct Costs | 97293.18 | 99212.98 | 96269.45 | 100063.43 | 1919.8 | 1.973% | -2943.53 | 0.97033
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-07-01 | Labor | 575411.66 | 568425.42 | 585731.28 | 569134.72 | -6986.24 | -1.214% | 17305.86 | 1.0304
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-07-01 | Materials | 445592.12 | 499509.3 | 451312.63 | 479129.28 | 53917.18 | 12.1% | -48196.67 | 0.90351
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-07-01 | Subcontracts | 349967.39 | 360627.55 | 343266.62 | 361611.98 | 10660.16 | 3.046% | -17360.93 | 0.95186
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-07-01 | Overhead | 269476.37 | 274091.63 | 265610.83 | 276751.5 | 4615.26 | 1.713% | -8480.8 | 0.96906
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-07-01 | Travel | 64577.88 | 66045.23 | 66166.82 | 66230.77 | 1467.35 | 2.272% | 121.59 | 1.0018
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-07-01 | Other Direct Costs | 99205.24 | 95845.26 | 97210.19 | 96756.2 | -3359.98 | -3.387% | 1364.93 | 1.0142
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-08-01 | Labor | 576965.81 | 590662.43 | 572219.76 | 588757.62 | 13696.62 | 2.374% | -18442.67 | 0.96878
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-08-01 | Materials | 457795.63 | 506752.59 | 461303.38 | 492222.47 | 48956.96 | 10.69% | -45449.21 | 0.91031
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-08-01 | Subcontracts | 368906.64 | 360566.75 | 363369.88 | 360609.22 | -8339.89 | -2.261% | 2803.13 | 1.0078
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-08-01 | Overhead | 266519.23 | 272589.85 | 264124.14 | 274656.13 | 6070.62 | 2.278% | -8465.71 | 0.96894
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-08-01 | Travel | 64361.36 | 64044.39 | 64309.39 | 64642.14 | -316.97 | -0.4925% | 265 | 1.0041
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-08-01 | Other Direct Costs | 99942.73 | 98578.01 | 97330.72 | 98627.25 | -1364.72 | -1.366% | -1247.29 | 0.98735
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-09-01 | Labor | 594628.91 | 581673.59 | 577797.7 | 585273.53 | -12955.32 | -2.179% | -3875.89 | 0.99334
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-09-01 | Materials | 462605.54 | 494781.52 | 452610.03 | 478717.08 | 32175.98 | 6.955% | -42171.49 | 0.91477
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-09-01 | Subcontracts | 362603.87 | 368520.17 | 358397.5 | 365590.98 | 5916.3 | 1.632% | -10122.67 | 0.97253
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-09-01 | Overhead | 266292.03 | 265993.89 | 267600.31 | 266887.18 | -298.14 | -0.112% | 1606.42 | 1.006
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-09-01 | Travel | 62775.72 | 61323.45 | 61855.58 | 62534.81 | -1452.27 | -2.313% | 532.13 | 1.0087
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-09-01 | Other Direct Costs | 97586.68 | 98286.49 | 98320.38 | 99347.95 | 699.81 | 0.7171% | 33.89 | 1.0003
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-10-01 | Labor | 600307.72 | 596580.83 | 616027.15 | 603470.42 | -3726.89 | -0.6208% | 19446.32 | 1.0326
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-10-01 | Materials | 484253.16 | 543378.01 | 473487.58 | 521380.7 | 59124.85 | 12.21% | -69890.43 | 0.87138
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-10-01 | Subcontracts | 374281.93 | 399781.7 | 373118.36 | 392418.77 | 25499.77 | 6.813% | -26663.34 | 0.93331
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-10-01 | Overhead | 260022.48 | 252158.23 | 262950.56 | 256924.93 | -7864.25 | -3.024% | 10792.33 | 1.0428
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-10-01 | Travel | 66307.88 | 65402.24 | 67556.83 | 65789.71 | -905.64 | -1.366% | 2154.59 | 1.0329
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-10-01 | Other Direct Costs | 101724.55 | 102834.19 | 98861.37 | 101357.78 | 1109.64 | 1.091% | -3972.82 | 0.96137
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-11-01 | Labor | 615140.09 | 602611.57 | 610022.59 | 607352.97 | -12528.52 | -2.037% | 7411.02 | 1.0123
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-11-01 | Materials | 474094.67 | 529910.54 | 485395.9 | 506405.26 | 55815.87 | 11.77% | -44514.64 | 0.916
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-11-01 | Subcontracts | 362322.8 | 379427.05 | 357836.02 | 371325.98 | 17104.25 | 4.721% | -21591.03 | 0.9431
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-11-01 | Overhead | 276096.54 | 268995.56 | 278544.47 | 275971.4 | -7100.98 | -2.572% | 9548.91 | 1.0355
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-11-01 | Travel | 67003.3 | 65328.06 | 68464.42 | 65654.02 | -1675.24 | -2.5% | 3136.36 | 1.048
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-11-01 | Other Direct Costs | 96678.74 | 97887.3 | 96025.73 | 96708.13 | 1208.56 | 1.25% | -1861.57 | 0.98098
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-12-01 | Labor | 598245.56 | 582475.64 | 581059.94 | 594779.75 | -15769.92 | -2.636% | -1415.7 | 0.99757
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-12-01 | Materials | 486191.13 | 561007.51 | 478412.09 | 534091.61 | 74816.38 | 15.39% | -82595.42 | 0.85277
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-12-01 | Subcontracts | 367528.95 | 383236.54 | 361135.81 | 380971.9 | 15707.59 | 4.274% | -22100.73 | 0.94233
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-12-01 | Overhead | 279769.86 | 274311.49 | 280535.65 | 278089.51 | -5458.37 | -1.951% | 6224.16 | 1.0227
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-12-01 | Travel | 67472.78 | 65687.26 | 68907.71 | 66175.56 | -1785.52 | -2.646% | 3220.45 | 1.049
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2024-12-01 | Other Direct Costs | 103589.22 | 105531.55 | 101650.55 | 106003.17 | 1942.33 | 1.875% | -3881 | 0.96322
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-01-01 | Labor | 567702.59 | 556779.98 | 574811.36 | 562530.5 | -10922.61 | -1.924% | 18031.38 | 1.0324
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-01-01 | Materials | 462788.64 | 531122.54 | 473544.43 | 510000.31 | 68333.9 | 14.77% | -57578.11 | 0.89159
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-01-01 | Subcontracts | 346859.3 | 369488.72 | 342740.07 | 367001.93 | 22629.42 | 6.524% | -26748.65 | 0.92761
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-01-01 | Overhead | 257392.65 | 248868.94 | 252760.93 | 250961.78 | -8523.71 | -3.312% | 3891.99 | 1.0156
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-01-01 | Travel | 60247.49 | 62181.58 | 59013.88 | 60842.17 | 1934.09 | 3.21% | -3167.7 | 0.94906
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-01-01 | Other Direct Costs | 94664.86 | 97515.63 | 93296.45 | 95645.21 | 2850.77 | 3.011% | -4219.18 | 0.95673
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-02-01 | Labor | 586512.82 | 583929.19 | 601340.73 | 591846.09 | -2583.63 | -0.4405% | 17411.54 | 1.0298
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-02-01 | Materials | 467230.25 | 526108.78 | 462937.21 | 512689.68 | 58878.53 | 12.6% | -63171.57 | 0.87993
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-02-01 | Subcontracts | 368380.92 | 385790.51 | 376181.4 | 385152.44 | 17409.59 | 4.726% | -9609.11 | 0.97509
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-02-01 | Overhead | 258637.35 | 255124.57 | 257465.75 | 258843.29 | -3512.78 | -1.358% | 2341.18 | 1.0092
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-02-01 | Travel | 61735.79 | 62841.83 | 61081.93 | 62274.46 | 1106.04 | 1.792% | -1759.9 | 0.97199
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-02-01 | Other Direct Costs | 93162.13 | 96412.07 | 92652.66 | 95968.82 | 3249.94 | 3.488% | -3759.41 | 0.96101
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-03-01 | Labor | 571901 | 584964.1 | 577759.33 | 583281.47 | 13063.1 | 2.284% | -7204.77 | 0.98768
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-03-01 | Materials | 454914.67 | 508892.43 | 466906.75 | 491328.08 | 53977.76 | 11.87% | -41985.68 | 0.9175
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-03-01 | Subcontracts | 372074.34 | 394764.53 | 374874.42 | 386352.3 | 22690.19 | 6.098% | -19890.11 | 0.94962
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-03-01 | Overhead | 272206.25 | 275849.48 | 276121.99 | 274463.43 | 3643.23 | 1.338% | 272.51 | 1.001
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-03-01 | Travel | 64545.09 | 64505.14 | 64833.66 | 64683.62 | -39.95 | -0.06189% | 328.52 | 1.0051
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-03-01 | Other Direct Costs | 94650.38 | 94209.25 | 97392.61 | 93522.75 | -441.13 | -0.4661% | 3183.36 | 1.0338
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-04-01 | Labor | 569503.25 | 577692.95 | 563364.19 | 576451.95 | 8189.7 | 1.438% | -14328.76 | 0.9752
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-04-01 | Materials | 458797.6 | 527307.37 | 451124.19 | 509662.81 | 68509.77 | 14.93% | -76183.18 | 0.85552
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-04-01 | Subcontracts | 381702.18 | 396869.99 | 391691.83 | 394907.4 | 15167.81 | 3.974% | -5178.16 | 0.98695
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-04-01 | Overhead | 264043.91 | 272610.6 | 267592.27 | 269709.5 | 8566.69 | 3.244% | -5018.33 | 0.98159
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-04-01 | Travel | 62363.77 | 64218.84 | 63834.4 | 63389.51 | 1855.07 | 2.975% | -384.44 | 0.99401
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-04-01 | Other Direct Costs | 99447.74 | 96380.03 | 97092.74 | 99241.35 | -3067.71 | -3.085% | 712.71 | 1.0074
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-05-01 | Labor | 613342.94 | 613490.79 | 609205.74 | 615416.34 | 147.85 | 0.02411% | -4285.05 | 0.99302
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-05-01 | Materials | 455601.44 | 507422.89 | 453227.91 | 489518.43 | 51821.45 | 11.37% | -54194.98 | 0.8932
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-05-01 | Subcontracts | 357020.76 | 385014.47 | 349860.08 | 374519.69 | 27993.71 | 7.841% | -35154.39 | 0.90869
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-05-01 | Overhead | 277822.1 | 285111.1 | 276050.36 | 285782.74 | 7289 | 2.624% | -9060.74 | 0.96822
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-05-01 | Travel | 66316.6 | 68528.33 | 67459.18 | 67189.95 | 2211.73 | 3.335% | -1069.15 | 0.9844
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-05-01 | Other Direct Costs | 96942.18 | 97633.27 | 94704.39 | 98618.82 | 691.09 | 0.7129% | -2928.88 | 0.97
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-06-01 | Labor | 595844.74 | 609033.94 | 581406.21 | 607572.41 | 13189.2 | 2.214% | -27627.73 | 0.95464
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-06-01 | Materials | 481590.95 | 541477.02 | 481226.43 | 521601.84 | 59886.07 | 12.44% | -60250.59 | 0.88873
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-06-01 | Subcontracts | 359383.56 | 397428.87 | 349842.17 | 386325.71 | 38045.31 | 10.59% | -47586.7 | 0.88026
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-06-01 | Overhead | 266799.87 | 263539.6 | 269671.79 | 262173.36 | -3260.27 | -1.222% | 6132.19 | 1.0233
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-06-01 | Travel | 65021.48 | 66974.45 | 66474.1 | 66778.14 | 1952.97 | 3.004% | -500.35 | 0.99253
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-06-01 | Other Direct Costs | 100913.17 | 97655.64 | 99105.21 | 98170.91 | -3257.53 | -3.228% | 1449.57 | 1.0148
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-07-01 | Labor | 607325.73 | 627467.38 | 597264.98 | 627832.59 | 20141.65 | 3.316% | -30202.4 | 0.95187
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-07-01 | Materials | 494641.26 | 557743.17 | 508886.14 | 532837.42 | 63101.91 | 12.76% | -48857.03 | 0.9124
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-07-01 | Subcontracts | 374756.78 | 380569.67 | 367502.65 | 375041.21 | 5812.89 | 1.551% | -13067.02 | 0.96566
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-07-01 | Overhead | 281786.4 | 291013.76 | 281146.86 | 291526.24 | 9227.36 | 3.275% | -9866.9 | 0.96609
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-07-01 | Travel | 63908.76 | 65216.26 | 65525.15 | 65282.08 | 1307.5 | 2.046% | 308.89 | 1.0047
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-07-01 | Other Direct Costs | 101657.17 | 99443.05 | 103034.24 | 101189.92 | -2214.12 | -2.178% | 3591.19 | 1.0361
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-08-01 | Labor | 639108.08 | 644857.13 | 625230.68 | 652018.23 | 5749.05 | 0.8995% | -19626.45 | 0.96956
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-08-01 | Materials | 501571.56 | 534439.17 | 504819.11 | 522820.92 | 32867.61 | 6.553% | -29620.06 | 0.94458
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-08-01 | Subcontracts | 369063.9 | 406021.37 | 377092.09 | 391000.39 | 36957.47 | 10.01% | -28929.28 | 0.92875
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-08-01 | Overhead | 277201.29 | 272763.63 | 279862.98 | 278190.25 | -4437.66 | -1.601% | 7099.35 | 1.026
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-08-01 | Travel | 66641.31 | 66406.6 | 65020.29 | 66429.46 | -234.71 | -0.3522% | -1386.31 | 0.97912
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-08-01 | Other Direct Costs | 103883.39 | 105872.24 | 105723.02 | 106412.49 | 1988.85 | 1.915% | -149.22 | 0.99859
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-09-01 | Labor | 642703.79 | 656750.36 | 627959.75 | 660819.42 | 14046.57 | 2.186% | -28790.61 | 0.95616
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-09-01 | Materials | 501435.21 | 539416.39 | 494710.13 | 526857.79 | 37981.18 | 7.574% | -44706.26 | 0.91712
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-09-01 | Subcontracts | 393119.13 | 414784.29 | 391844.92 | 404368.33 | 21665.16 | 5.511% | -22939.37 | 0.9447
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-09-01 | Overhead | 279984.69 | 288372.31 | 274209.34 | 282836.42 | 8387.62 | 2.996% | -14162.97 | 0.95089
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-09-01 | Travel | 64427.9 | 64070.95 | 64791.31 | 64322.68 | -356.95 | -0.554% | 720.36 | 1.0112
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-09-01 | Other Direct Costs | 105593.33 | 103163.75 | 105027.11 | 102886.91 | -2429.58 | -2.301% | 1863.36 | 1.0181
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-10-01 | Labor | 619831.19 | 622849.98 | 637974.71 | 616478.44 | 3018.79 | 0.487% | 15124.73 | 1.0243
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-10-01 | Materials | 473725.93 | 555538.65 | 478269.19 | 526580.47 | 81812.72 | 17.27% | -77269.46 | 0.86091
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-10-01 | Subcontracts | 391748.21 | 420595.13 | 384738.79 | 406352.22 | 28846.92 | 7.364% | -35856.34 | 0.91475
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-10-01 | Overhead | 284776.91 | 286235.34 | 276609.64 | 286896.53 | 1458.43 | 0.5121% | -9625.7 | 0.96637
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-10-01 | Travel | 64440.37 | 65899.95 | 64768.32 | 65298.08 | 1459.58 | 2.265% | -1131.63 | 0.98283
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-10-01 | Other Direct Costs | 101855.85 | 103688.46 | 102803.29 | 102257.29 | 1832.61 | 1.799% | -885.17 | 0.99146
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-11-01 | Labor | 624346.67 | 641349.29 | 625356.76 | 646213.83 | 17002.62 | 2.723% | -15992.53 | 0.97506
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-11-01 | Materials | 513712.92 | 552471.47 | 514172.29 | 539821.23 | 38758.55 | 7.545% | -38299.18 | 0.93068
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-11-01 | Subcontracts | 402446.96 | 425120.15 | 405898.62 | 413095.71 | 22673.19 | 5.634% | -19221.53 | 0.95479
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-11-01 | Overhead | 279385.85 | 281153.25 | 286460.6 | 285466.28 | 1767.4 | 0.6326% | 5307.35 | 1.0189
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-11-01 | Travel | 66116.38 | 66231.11 | 67357.57 | 65720.98 | 114.73 | 0.1735% | 1126.46 | 1.017
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-11-01 | Other Direct Costs | 107580.73 | 109529.38 | 105246.41 | 110399.31 | 1948.65 | 1.811% | -4282.97 | 0.9609
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-12-01 | Labor | 639996.92 | 617985.43 | 633227.39 | 625404.81 | -22011.49 | -3.439% | 15241.96 | 1.0247
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-12-01 | Materials | 494236.17 | 554017.73 | 482906.44 | 539640.06 | 59781.56 | 12.1% | -71111.29 | 0.87164
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-12-01 | Subcontracts | 409535.69 | 425821.33 | 412519.22 | 416189.18 | 16285.64 | 3.977% | -13302.11 | 0.96876
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-12-01 | Overhead | 296546.99 | 306512.23 | 290516.17 | 301682.37 | 9965.24 | 3.36% | -15996.06 | 0.94781
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-12-01 | Travel | 69731.33 | 71008.35 | 68525.89 | 70004.64 | 1277.02 | 1.831% | -2482.46 | 0.96504
AP-103 | Orion | NASA | Space Systems | Elena Torres | 2025-12-01 | Other Direct Costs | 105760.21 | 104759.71 | 105919.79 | 106696.28 | -1000.5 | -0.946% | 1160.08 | 1.0111
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-01-01 | Labor | 354684.69 | 359570.9 | 355040.32 | 355465.5 | 4886.21 | 1.378% | -4530.58 | 0.9874
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-01-01 | Materials | 282812.54 | 273564.81 | 283249.96 | 276818.89 | -9247.73 | -3.27% | 9685.15 | 1.0354
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-01-01 | Subcontracts | 224324.56 | 216484.06 | 226291.85 | 220481.04 | -7840.5 | -3.495% | 9807.79 | 1.0453
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-01-01 | Overhead | 159604.14 | 163146.14 | 157804.23 | 160867.68 | 3542 | 2.219% | -5341.91 | 0.96726
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-01-01 | Travel | 38503.89 | 38719.59 | 37438.02 | 38307.37 | 215.7 | 0.5602% | -1281.57 | 0.9669
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-01-01 | Other Direct Costs | 62665.77 | 64011.69 | 63033.22 | 64433.27 | 1345.92 | 2.148% | -978.47 | 0.98471
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-02-01 | Labor | 362011.2 | 367222.26 | 355922.91 | 364686.27 | 5211.06 | 1.439% | -11299.35 | 0.96923
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-02-01 | Materials | 283714.76 | 291619.83 | 282455.87 | 289092.46 | 7905.07 | 2.786% | -9163.96 | 0.96858
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-02-01 | Subcontracts | 228392.81 | 222098.11 | 229088.23 | 228303.47 | -6294.7 | -2.756% | 6990.12 | 1.0315
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-02-01 | Overhead | 171615.88 | 172121.83 | 172933.9 | 173784.11 | 505.95 | 0.2948% | 812.07 | 1.0047
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-02-01 | Travel | 40809.24 | 39841.11 | 41515.98 | 40695.11 | -968.13 | -2.372% | 1674.87 | 1.042
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-02-01 | Other Direct Costs | 61196.11 | 62254.91 | 62746.96 | 62942.14 | 1058.8 | 1.73% | 492.05 | 1.0079
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-03-01 | Labor | 365890.44 | 363644.36 | 364305.75 | 362316.65 | -2246.08 | -0.6139% | 661.39 | 1.0018
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-03-01 | Materials | 300612.01 | 295084.5 | 299282.06 | 294120.2 | -5527.51 | -1.839% | 4197.56 | 1.0142
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-03-01 | Subcontracts | 234013 | 238688.32 | 227077.34 | 238866.5 | 4675.32 | 1.998% | -11610.98 | 0.95136
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-03-01 | Overhead | 173498.54 | 175343.56 | 171361.04 | 176396.35 | 1845.02 | 1.063% | -3982.52 | 0.97729
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-03-01 | Travel | 39009.84 | 38780.52 | 39419.98 | 39166.53 | -229.32 | -0.5879% | 639.46 | 1.0165
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-03-01 | Other Direct Costs | 60020.69 | 58772.06 | 58659.73 | 58606.11 | -1248.63 | -2.08% | -112.33 | 0.99809
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-04-01 | Labor | 386096.81 | 395559.19 | 392791.85 | 396646.09 | 9462.38 | 2.451% | -2767.34 | 0.993
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-04-01 | Materials | 308000.64 | 311203.49 | 304165.89 | 309780.76 | 3202.85 | 1.04% | -7037.6 | 0.97739
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-04-01 | Subcontracts | 233224.62 | 228158.66 | 227935.75 | 233097.54 | -5065.96 | -2.172% | -222.91 | 0.99902
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-04-01 | Overhead | 173606.17 | 172776.47 | 175762.61 | 172783.16 | -829.7 | -0.4779% | 2986.14 | 1.0173
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-04-01 | Travel | 40515.38 | 41149.04 | 40842.45 | 41420.93 | 633.66 | 1.564% | -306.59 | 0.99255
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-04-01 | Other Direct Costs | 62477.53 | 61442.95 | 62744.05 | 62879.76 | -1034.58 | -1.656% | 1301.1 | 1.0212
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-05-01 | Labor | 387079.65 | 395526.16 | 380138.5 | 388234.63 | 8446.51 | 2.182% | -15387.66 | 0.9611
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-05-01 | Materials | 294498.57 | 294207.17 | 287822.53 | 298858.25 | -291.4 | -0.09895% | -6384.64 | 0.9783
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-05-01 | Subcontracts | 227737.07 | 223720.46 | 232482.14 | 227698.5 | -4016.61 | -1.764% | 8761.68 | 1.0392
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-05-01 | Overhead | 174563.35 | 168767 | 172016.96 | 169193.63 | -5796.35 | -3.32% | 3249.96 | 1.0193
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-05-01 | Travel | 40693.95 | 40382.97 | 40231.56 | 40711.68 | -310.98 | -0.7642% | -151.41 | 0.99625
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-05-01 | Other Direct Costs | 64208.44 | 63529.99 | 65933.33 | 64840.86 | -678.45 | -1.057% | 2403.34 | 1.0378
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-06-01 | Labor | 376953.25 | 376032.86 | 377620.14 | 377821.4 | -920.39 | -0.2442% | 1587.28 | 1.0042
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-06-01 | Materials | 297805.98 | 293349.19 | 304127.62 | 300015.04 | -4456.79 | -1.497% | 10778.43 | 1.0367
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-06-01 | Subcontracts | 242310.96 | 238596.75 | 244589.7 | 238763.16 | -3714.21 | -1.533% | 5992.95 | 1.0251
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-06-01 | Overhead | 177832.98 | 176022.12 | 181585.95 | 175857.57 | -1810.86 | -1.018% | 5563.83 | 1.0316
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-06-01 | Travel | 41201.1 | 41175.07 | 41120.86 | 41576.28 | -26.03 | -0.06318% | -54.21 | 0.99868
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-06-01 | Other Direct Costs | 63984.03 | 65795.56 | 63472.48 | 65528.87 | 1811.53 | 2.831% | -2323.08 | 0.96469
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-07-01 | Labor | 400370.22 | 410741.3 | 407465.84 | 403964.46 | 10371.08 | 2.59% | -3275.46 | 0.99203
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-07-01 | Materials | 316130.48 | 309806.34 | 322763.42 | 309818.03 | -6324.14 | -2% | 12957.08 | 1.0418
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-07-01 | Subcontracts | 247811.59 | 246006.93 | 247691.07 | 244292.22 | -1804.66 | -0.7282% | 1684.14 | 1.0068
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-07-01 | Overhead | 178834.36 | 177467.04 | 179891.24 | 180334.91 | -1367.32 | -0.7646% | 2424.2 | 1.0137
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-07-01 | Travel | 41046.65 | 41469.26 | 40959.89 | 42036.98 | 422.61 | 1.03% | -509.37 | 0.98772
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-07-01 | Other Direct Costs | 64298.28 | 65351.21 | 66118.18 | 65559.85 | 1052.93 | 1.638% | 766.97 | 1.0117
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-08-01 | Labor | 388051.13 | 401181.91 | 396401.68 | 400411.33 | 13130.78 | 3.384% | -4780.23 | 0.98808
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-08-01 | Materials | 299417.49 | 295309.1 | 301626.77 | 299219.5 | -4108.39 | -1.372% | 6317.67 | 1.0214
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-08-01 | Subcontracts | 243548.45 | 237006.75 | 244628.32 | 239849.39 | -6541.7 | -2.686% | 7621.57 | 1.0322
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-08-01 | Overhead | 174794.61 | 176322.94 | 174848.8 | 174060.94 | 1528.33 | 0.8744% | -1474.14 | 0.99164
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-08-01 | Travel | 41322.11 | 41264.87 | 40955.73 | 41134.76 | -57.24 | -0.1385% | -309.14 | 0.99251
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-08-01 | Other Direct Costs | 66083.17 | 66006.12 | 65729.16 | 65864.38 | -77.05 | -0.1166% | -276.96 | 0.9958
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-09-01 | Labor | 396685.92 | 408418.91 | 372890.22 | 403506.2 | 11732.99 | 2.958% | -35528.69 | 0.91301
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-09-01 | Materials | 322604.93 | 312766.52 | 308912.4 | 318079.47 | -9838.41 | -3.05% | -3854.12 | 0.98768
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-09-01 | Subcontracts | 253282.4 | 255074.02 | 237796.36 | 258644.08 | 1791.62 | 0.7074% | -17277.66 | 0.93226
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-09-01 | Overhead | 175450.49 | 174759.56 | 168690.54 | 175489.03 | -690.93 | -0.3938% | -6069.02 | 0.96527
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-09-01 | Travel | 43042.39 | 43698.13 | 39384.93 | 43723.31 | 655.74 | 1.523% | -4313.2 | 0.9013
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-09-01 | Other Direct Costs | 63493.26 | 64814.87 | 58290.22 | 64540.41 | 1321.61 | 2.081% | -6524.65 | 0.89933
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-10-01 | Labor | 401075.87 | 398620.16 | 379815.33 | 396526.17 | -2455.71 | -0.6123% | -18804.83 | 0.95283
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-10-01 | Materials | 308594.78 | 306510.12 | 299409.31 | 308448.25 | -2084.66 | -0.6755% | -7100.81 | 0.97683
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-10-01 | Subcontracts | 247965.62 | 251343.41 | 235790.08 | 249086.52 | 3377.79 | 1.362% | -15553.33 | 0.93812
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-10-01 | Overhead | 181612.19 | 181929.59 | 175799.02 | 179924.51 | 317.4 | 0.1748% | -6130.57 | 0.9663
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-10-01 | Travel | 42532.24 | 41581.66 | 41157.39 | 41893.31 | -950.58 | -2.235% | -424.27 | 0.9898
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-10-01 | Other Direct Costs | 66433.7 | 67129.57 | 63884.96 | 67122.98 | 695.87 | 1.047% | -3244.61 | 0.95167
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-11-01 | Labor | 405426.79 | 403995.84 | 373310.67 | 403881.89 | -1430.95 | -0.3529% | -30685.17 | 0.92405
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-11-01 | Materials | 323631.76 | 316730.34 | 313364.12 | 321058.79 | -6901.42 | -2.132% | -3366.22 | 0.98937
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-11-01 | Subcontracts | 250726.42 | 255306.89 | 233295.3 | 255050.37 | 4580.47 | 1.827% | -22011.59 | 0.91378
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-11-01 | Overhead | 185994.06 | 191445.66 | 175275.01 | 192054.89 | 5451.6 | 2.931% | -16170.65 | 0.91553
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-11-01 | Travel | 43169 | 44208.86 | 40988.09 | 43645.66 | 1039.86 | 2.409% | -3220.77 | 0.92715
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-11-01 | Other Direct Costs | 68964.58 | 68144.62 | 65476.99 | 68052.91 | -819.96 | -1.189% | -2667.63 | 0.96085
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-12-01 | Labor | 402008.38 | 400198.38 | 369699.69 | 398243.11 | -1810 | -0.4502% | -30498.69 | 0.92379
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-12-01 | Materials | 320520.17 | 321938.98 | 296294.17 | 320550.11 | 1418.81 | 0.4427% | -25644.81 | 0.92034
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-12-01 | Subcontracts | 241728.43 | 237721.42 | 224943.28 | 238529.82 | -4007.01 | -1.658% | -12778.14 | 0.94625
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-12-01 | Overhead | 181546.14 | 178699.85 | 170505.12 | 181456.63 | -2846.29 | -1.568% | -8194.73 | 0.95414
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-12-01 | Travel | 42999.04 | 43861.15 | 41092.41 | 43299.06 | 862.11 | 2.005% | -2768.74 | 0.93687
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2024-12-01 | Other Direct Costs | 69651.03 | 69763.98 | 66039.79 | 68903.8 | 112.95 | 0.1622% | -3724.19 | 0.94662
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-01-01 | Labor | 372259.71 | 361822.09 | 358829.74 | 371343.01 | -10437.62 | -2.804% | -2992.35 | 0.99173
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-01-01 | Materials | 302968.86 | 311632.15 | 289858.14 | 306714.74 | 8663.29 | 2.859% | -21774.01 | 0.93013
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-01-01 | Subcontracts | 229390.28 | 231004.18 | 214674.77 | 234351.72 | 1613.9 | 0.7036% | -16329.41 | 0.92931
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-01-01 | Overhead | 169914.82 | 171823.68 | 161602.36 | 173935.78 | 1908.86 | 1.123% | -10221.32 | 0.94051
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-01-01 | Travel | 42417.39 | 41963.73 | 40693.78 | 42108.44 | -453.66 | -1.07% | -1269.95 | 0.96974
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-01-01 | Other Direct Costs | 62703.58 | 62812.44 | 59161.31 | 62365.18 | 108.86 | 0.1736% | -3651.13 | 0.94187
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-02-01 | Labor | 399923.78 | 400184.18 | 375442.82 | 401374.87 | 260.4 | 0.06511% | -24741.36 | 0.93818
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-02-01 | Materials | 310395.69 | 301429.95 | 290177.9 | 304712.19 | -8965.74 | -2.888% | -11252.05 | 0.96267
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-02-01 | Subcontracts | 232107.29 | 235058.13 | 212801.47 | 233899.65 | 2950.84 | 1.271% | -22256.66 | 0.90531
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-02-01 | Overhead | 170985.29 | 171211.67 | 161898.7 | 171345.95 | 226.38 | 0.1324% | -9312.97 | 0.94561
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-02-01 | Travel | 43127.07 | 43767.22 | 39494.69 | 43156.69 | 640.15 | 1.484% | -4272.53 | 0.90238
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-02-01 | Other Direct Costs | 65245.12 | 65994.69 | 62189.49 | 64962.64 | 749.57 | 1.149% | -3805.2 | 0.94234
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-03-01 | Labor | 402603.56 | 409454.33 | 380467.14 | 404851.2 | 6850.77 | 1.702% | -28987.19 | 0.92921
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-03-01 | Materials | 315026.62 | 304471.85 | 292885.23 | 309969.71 | -10554.77 | -3.35% | -11586.62 | 0.96195
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-03-01 | Subcontracts | 237894.15 | 239100.58 | 215241.48 | 237629.24 | 1206.43 | 0.5071% | -23859.1 | 0.90021
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-03-01 | Overhead | 183514.3 | 181754.9 | 173141.21 | 182157.39 | -1759.4 | -0.9587% | -8613.69 | 0.95261
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-03-01 | Travel | 40823 | 39728.16 | 38214.52 | 40108.48 | -1094.84 | -2.682% | -1513.64 | 0.9619
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-03-01 | Other Direct Costs | 65620.74 | 67607.62 | 60457.52 | 67883.05 | 1986.88 | 3.028% | -7150.1 | 0.89424
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-04-01 | Labor | 382778.72 | 380605.57 | 362473.76 | 377102.55 | -2173.15 | -0.5677% | -18131.81 | 0.95236
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-04-01 | Materials | 312710.22 | 312797.92 | 296599.74 | 316361.98 | 87.7 | 0.02805% | -16198.18 | 0.94822
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-04-01 | Subcontracts | 251064.48 | 249996.53 | 237728.72 | 248451.79 | -1067.95 | -0.4254% | -12267.81 | 0.95093
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-04-01 | Overhead | 185885.85 | 190249.49 | 171926.36 | 191950.04 | 4363.64 | 2.347% | -18323.13 | 0.90369
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-04-01 | Travel | 43983.69 | 42778.31 | 41192.88 | 42964.69 | -1205.38 | -2.741% | -1585.43 | 0.96294
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-04-01 | Other Direct Costs | 63697.12 | 64066.64 | 57965.17 | 64509.8 | 369.52 | 0.5801% | -6101.47 | 0.90476
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-05-01 | Labor | 412053.85 | 400955.44 | 372038.29 | 412246.47 | -11098.41 | -2.693% | -28917.15 | 0.92788
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-05-01 | Materials | 319354.14 | 316169.19 | 297494.56 | 320369.56 | -3184.95 | -0.9973% | -18674.63 | 0.94093
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-05-01 | Subcontracts | 244827.73 | 251191.39 | 226683.9 | 248140.77 | 6363.66 | 2.599% | -24507.49 | 0.90243
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-05-01 | Overhead | 182246.27 | 176946 | 165983.11 | 178842.72 | -5300.27 | -2.908% | -10962.89 | 0.93804
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-05-01 | Travel | 43557.55 | 44398.33 | 39252.41 | 43996.03 | 840.78 | 1.93% | -5145.92 | 0.8841
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-05-01 | Other Direct Costs | 65749.46 | 66255.51 | 60788.86 | 66235.91 | 506.05 | 0.7697% | -5466.65 | 0.91749
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-06-01 | Labor | 397805.89 | 402210.01 | 377930.3 | 406948.29 | 4404.12 | 1.107% | -24279.71 | 0.93963
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-06-01 | Materials | 317996.71 | 322106.51 | 290163 | 325646.37 | 4109.8 | 1.292% | -31943.51 | 0.90083
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-06-01 | Subcontracts | 254943.13 | 254988.56 | 229061.06 | 255061.52 | 45.43 | 0.01782% | -25927.5 | 0.89832
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-06-01 | Overhead | 175350.23 | 176073.04 | 166939.57 | 177179.25 | 722.81 | 0.4122% | -9133.47 | 0.94813
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-06-01 | Travel | 43389.67 | 42470.04 | 39659.41 | 42763.05 | -919.63 | -2.119% | -2810.63 | 0.93382
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-06-01 | Other Direct Costs | 68552.41 | 66339.41 | 64543.64 | 67181.89 | -2213 | -3.228% | -1795.77 | 0.97293
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-07-01 | Labor | 394729.69 | 389349.36 | 355107.61 | 386711.65 | -5380.33 | -1.363% | -34241.75 | 0.91205
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-07-01 | Materials | 318143.16 | 316971.24 | 299249.37 | 313692.83 | -1171.92 | -0.3684% | -17721.87 | 0.94409
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-07-01 | Subcontracts | 249392.27 | 249170.99 | 232552.39 | 250653.3 | -221.28 | -0.08873% | -16618.6 | 0.9333
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-07-01 | Overhead | 186621.31 | 189640.44 | 175503.35 | 186345.22 | 3019.13 | 1.618% | -14137.09 | 0.92545
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-07-01 | Travel | 42613.31 | 42908.75 | 38726.98 | 43247.61 | 295.44 | 0.6933% | -4181.77 | 0.90254
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-07-01 | Other Direct Costs | 68352.6 | 70584.92 | 61661.71 | 70598.48 | 2232.32 | 3.266% | -8923.21 | 0.87358
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-08-01 | Labor | 417732.36 | 430519.59 | 376972.31 | 429287.88 | 12787.23 | 3.061% | -53547.28 | 0.87562
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-08-01 | Materials | 319807.45 | 312706.81 | 296975.48 | 314883.97 | -7100.64 | -2.22% | -15731.33 | 0.94969
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-08-01 | Subcontracts | 258983.97 | 262226.35 | 230223.79 | 265619.29 | 3242.38 | 1.252% | -32002.56 | 0.87796
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-08-01 | Overhead | 188656.07 | 184530.05 | 170232.93 | 185738.3 | -4126.02 | -2.187% | -14297.12 | 0.92252
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-08-01 | Travel | 43595.27 | 42740.14 | 40590.07 | 43248.05 | -855.13 | -1.962% | -2150.07 | 0.94969
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-08-01 | Other Direct Costs | 67836.7 | 68962.27 | 61326.09 | 67813.42 | 1125.57 | 1.659% | -7636.18 | 0.88927
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-09-01 | Labor | 409944.41 | 404332.76 | 386247.26 | 406304.62 | -5611.65 | -1.369% | -18085.5 | 0.95527
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-09-01 | Materials | 316759.73 | 307919.55 | 293825.43 | 309774.75 | -8840.18 | -2.791% | -14094.12 | 0.95423
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-09-01 | Subcontracts | 265381.98 | 258321.26 | 249921.62 | 263919.8 | -7060.72 | -2.661% | -8399.64 | 0.96748
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-09-01 | Overhead | 182099.12 | 178152.56 | 164360.19 | 182611.47 | -3946.56 | -2.167% | -13792.37 | 0.92258
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-09-01 | Travel | 42822.93 | 43374.61 | 39964.99 | 42812.46 | 551.68 | 1.288% | -3409.62 | 0.92139
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-09-01 | Other Direct Costs | 70232.64 | 71743.68 | 66217.64 | 71847.38 | 1511.04 | 2.151% | -5526.04 | 0.92298
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-10-01 | Labor | 424338.36 | 419543.14 | 375447.16 | 423082.51 | -4795.22 | -1.13% | -44095.98 | 0.8949
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-10-01 | Materials | 315475.92 | 306906.09 | 291342.04 | 309575.39 | -8569.83 | -2.716% | -15564.05 | 0.94929
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-10-01 | Subcontracts | 251125.04 | 257094.74 | 233079.89 | 258175.53 | 5969.7 | 2.377% | -24014.85 | 0.90659
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-10-01 | Overhead | 183183.67 | 182021.48 | 170466.57 | 185626.73 | -1162.19 | -0.6344% | -11554.91 | 0.93652
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-10-01 | Travel | 44040.2 | 43310.29 | 39983.72 | 44005.17 | -729.91 | -1.657% | -3326.57 | 0.92319
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-10-01 | Other Direct Costs | 67088.34 | 68550.11 | 59935.27 | 68620.83 | 1461.77 | 2.179% | -8614.84 | 0.87433
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-11-01 | Labor | 407567.08 | 403766.16 | 366638.79 | 410714.94 | -3800.92 | -0.9326% | -37127.37 | 0.90805
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-11-01 | Materials | 340504.97 | 330627.91 | 302328.57 | 339914.71 | -9877.06 | -2.901% | -28299.34 | 0.91441
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-11-01 | Subcontracts | 266217.94 | 259402.64 | 244672.55 | 259190.34 | -6815.3 | -2.56% | -14730.09 | 0.94322
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-11-01 | Overhead | 190440.33 | 183977.89 | 173764.49 | 185327.23 | -6462.44 | -3.393% | -10213.4 | 0.94449
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-11-01 | Travel | 46400.09 | 46784.75 | 41709.21 | 46632.09 | 384.66 | 0.829% | -5075.54 | 0.89151
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-11-01 | Other Direct Costs | 69145.77 | 68293.57 | 61452.67 | 68745.86 | -852.2 | -1.232% | -6840.9 | 0.89983
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-12-01 | Labor | 436048.01 | 437654.63 | 390815.2 | 439507.11 | 1606.62 | 0.3685% | -46839.43 | 0.89298
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-12-01 | Materials | 331375.89 | 331841.06 | 294587.36 | 329047.99 | 465.17 | 0.1404% | -37253.7 | 0.88774
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-12-01 | Subcontracts | 266960.26 | 261357.62 | 244571.16 | 263459.59 | -5602.64 | -2.099% | -16786.46 | 0.93577
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-12-01 | Overhead | 185194.79 | 184534.93 | 167970.07 | 185074.34 | -659.86 | -0.3563% | -16564.86 | 0.91023
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-12-01 | Travel | 44125.6 | 45467.27 | 39602.53 | 44955.53 | 1341.67 | 3.041% | -5864.74 | 0.87101
AP-104 | Atlas | Commercial | Satellite Systems | David Kim | 2025-12-01 | Other Direct Costs | 73509.21 | 72614.84 | 67874.21 | 72251.25 | -894.37 | -1.217% | -4740.63 | 0.93472
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-01-01 | Labor | 311261.63 | 336923.28 | 294078.84 | 329031.45 | 25661.65 | 8.244% | -42844.44 | 0.87284
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-01-01 | Materials | 244006.79 | 270474.98 | 230152.45 | 262173.59 | 26468.19 | 10.85% | -40322.53 | 0.85092
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-01-01 | Subcontracts | 190444.96 | 211688.08 | 186566.89 | 205414.25 | 21243.12 | 11.15% | -25121.19 | 0.88133
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-01-01 | Overhead | 147535.81 | 158970.34 | 141048.03 | 153690.47 | 11434.53 | 7.75% | -17922.31 | 0.88726
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-01-01 | Travel | 34600.92 | 37187.43 | 32746.54 | 36821.03 | 2586.51 | 7.475% | -4440.89 | 0.88058
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-01-01 | Other Direct Costs | 54346.23 | 57940.01 | 52349.89 | 56161.19 | 3593.78 | 6.613% | -5590.12 | 0.90352
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-02-01 | Labor | 331206.37 | 343705.05 | 326099.67 | 344390.62 | 12498.68 | 3.774% | -17605.38 | 0.94878
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-02-01 | Materials | 253749.3 | 260465.73 | 241556.56 | 259145.08 | 6716.43 | 2.647% | -18909.17 | 0.9274
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-02-01 | Subcontracts | 203069.8 | 215002.08 | 200423.5 | 213694.06 | 11932.28 | 5.876% | -14578.58 | 0.93219
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-02-01 | Overhead | 142872.37 | 158104 | 137501.78 | 155021.15 | 15231.63 | 10.66% | -20602.22 | 0.86969
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-02-01 | Travel | 33219.37 | 34932 | 31006.19 | 34577.1 | 1712.63 | 5.156% | -3925.81 | 0.88762
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-02-01 | Other Direct Costs | 52595.36 | 56604.66 | 52217.86 | 54873.16 | 4009.3 | 7.623% | -4386.8 | 0.9225
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-03-01 | Labor | 325189.82 | 340617.58 | 307536.87 | 340007.02 | 15427.76 | 4.744% | -33080.71 | 0.90288
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-03-01 | Materials | 256607 | 282414.66 | 241304.63 | 270894.77 | 25807.66 | 10.06% | -41110.03 | 0.85443
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-03-01 | Subcontracts | 206732.09 | 220375.08 | 201745.95 | 218305.65 | 13642.99 | 6.599% | -18629.13 | 0.91547
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-03-01 | Overhead | 144462.74 | 149695.64 | 138439.18 | 146514.82 | 5232.9 | 3.622% | -11256.46 | 0.9248
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-03-01 | Travel | 33748.87 | 35612.87 | 32643.06 | 35061.21 | 1864 | 5.523% | -2969.81 | 0.91661
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-03-01 | Other Direct Costs | 52024.77 | 53582.36 | 48427.43 | 52481.88 | 1557.59 | 2.994% | -5154.93 | 0.90379
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-04-01 | Labor | 315305.1 | 325776.42 | 295571.37 | 319300.31 | 10471.32 | 3.321% | -30205.05 | 0.90728
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-04-01 | Materials | 248341.44 | 269486.82 | 238289.74 | 266340.17 | 21145.38 | 8.515% | -31197.08 | 0.88424
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-04-01 | Subcontracts | 204454.09 | 217064.55 | 197860.34 | 214985.59 | 12610.46 | 6.168% | -19204.21 | 0.91153
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-04-01 | Overhead | 146321.61 | 158246.74 | 138350.15 | 156011.37 | 11925.13 | 8.15% | -19896.59 | 0.87427
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-04-01 | Travel | 34464.5 | 34972.6 | 32654.19 | 34417.96 | 508.1 | 1.474% | -2318.41 | 0.93371
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-04-01 | Other Direct Costs | 54781.61 | 57082.82 | 53770.26 | 56176.05 | 2301.21 | 4.201% | -3312.56 | 0.94197
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-05-01 | Labor | 335879.29 | 349983.12 | 323489.12 | 347588.56 | 14103.83 | 4.199% | -26494 | 0.9243
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-05-01 | Materials | 255061.21 | 269295.33 | 239223.73 | 267959.44 | 14234.12 | 5.581% | -30071.6 | 0.88833
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-05-01 | Subcontracts | 208012.3 | 218150 | 201892.06 | 215761.04 | 10137.7 | 4.874% | -16257.94 | 0.92547
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-05-01 | Overhead | 148490.32 | 159489.53 | 141061.43 | 156295.58 | 10999.21 | 7.407% | -18428.1 | 0.88446
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-05-01 | Travel | 34325.18 | 36023.24 | 34141.15 | 35988.02 | 1698.06 | 4.947% | -1882.09 | 0.94775
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-05-01 | Other Direct Costs | 53455.25 | 58982.69 | 50664.1 | 57566.88 | 5527.44 | 10.34% | -8318.59 | 0.85897
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-06-01 | Labor | 322501.04 | 354865.09 | 310369.06 | 348563.96 | 32364.05 | 10.04% | -44496.03 | 0.87461
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-06-01 | Materials | 260051.13 | 277275.6 | 242551.24 | 269859.41 | 17224.47 | 6.623% | -34724.36 | 0.87477
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-06-01 | Subcontracts | 201922.41 | 212989.57 | 196835.64 | 208214.45 | 11067.16 | 5.481% | -16153.93 | 0.92416
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-06-01 | Overhead | 153118.69 | 161825.27 | 150851.21 | 159734.03 | 8706.58 | 5.686% | -10974.06 | 0.93219
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-06-01 | Travel | 35678.29 | 36521.41 | 33992.01 | 36768.65 | 843.12 | 2.363% | -2529.4 | 0.93074
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-06-01 | Other Direct Costs | 54468.01 | 56770.8 | 52364 | 56208.27 | 2302.79 | 4.228% | -4406.8 | 0.92238
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-07-01 | Labor | 330038.92 | 350246.75 | 307195.16 | 346504.16 | 20207.83 | 6.123% | -43051.59 | 0.87708
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-07-01 | Materials | 272065.86 | 275793.29 | 268815.37 | 272487.26 | 3727.43 | 1.37% | -6977.92 | 0.9747
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-07-01 | Subcontracts | 216177.29 | 229020.38 | 214628.14 | 224548.52 | 12843.09 | 5.941% | -14392.24 | 0.93716
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-07-01 | Overhead | 155795.89 | 160377.55 | 150175.8 | 160406.13 | 4581.66 | 2.941% | -10201.75 | 0.93639
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-07-01 | Travel | 34776.36 | 35748.79 | 32610.84 | 35926.72 | 972.43 | 2.796% | -3137.95 | 0.91222
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-07-01 | Other Direct Costs | 57867.97 | 60888.62 | 53541.46 | 59441.06 | 3020.65 | 5.22% | -7347.16 | 0.87933
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-08-01 | Labor | 346731.92 | 366605.2 | 327665.66 | 363452.16 | 19873.28 | 5.732% | -38939.54 | 0.89378
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-08-01 | Materials | 274118.82 | 288884.53 | 254185.76 | 284087.92 | 14765.71 | 5.387% | -34698.77 | 0.87989
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-08-01 | Subcontracts | 210386.28 | 220777.12 | 202174.83 | 215899.27 | 10390.84 | 4.939% | -18602.29 | 0.91574
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-08-01 | Overhead | 151672.8 | 162424.71 | 145410.92 | 157500.39 | 10751.91 | 7.089% | -17013.79 | 0.89525
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-08-01 | Travel | 37401.31 | 40120.31 | 34923.45 | 38851.57 | 2719 | 7.27% | -5196.86 | 0.87047
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-08-01 | Other Direct Costs | 56627.64 | 59725.1 | 55782.92 | 58096 | 3097.46 | 5.47% | -3942.18 | 0.93399
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-09-01 | Labor | 340798.26 | 350191.73 | 332748.46 | 346137.49 | 9393.47 | 2.756% | -17443.27 | 0.95019
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-09-01 | Materials | 266108.19 | 280008.93 | 255513.39 | 277195.11 | 13900.74 | 5.224% | -24495.54 | 0.91252
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-09-01 | Subcontracts | 209370.9 | 227036.87 | 203284.98 | 223447.21 | 17665.97 | 8.438% | -23751.89 | 0.89538
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-09-01 | Overhead | 160243.77 | 166537.38 | 148831.06 | 164843.12 | 6293.61 | 3.928% | -17706.32 | 0.89368
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-09-01 | Travel | 37200.03 | 41275.52 | 34814.43 | 39772.62 | 4075.49 | 10.96% | -6461.09 | 0.84346
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-09-01 | Other Direct Costs | 55845.76 | 58775.93 | 54180.97 | 58432.14 | 2930.17 | 5.247% | -4594.96 | 0.92182
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-10-01 | Labor | 338727.44 | 336396.53 | 341381.25 | 341001.84 | -2330.91 | -0.6881% | 4984.72 | 1.0148
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-10-01 | Materials | 267351.11 | 270837.28 | 269852.48 | 272152.81 | 3486.17 | 1.304% | -984.8 | 0.99636
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-10-01 | Subcontracts | 211295.94 | 208709.8 | 216904.87 | 211925.47 | -2586.14 | -1.224% | 8195.07 | 1.0393
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-10-01 | Overhead | 151726.51 | 152706.48 | 153850.66 | 152974.13 | 979.97 | 0.6459% | 1144.18 | 1.0075
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-10-01 | Travel | 36479.41 | 36339.93 | 36953.46 | 36674.39 | -139.48 | -0.3824% | 613.53 | 1.0169
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-10-01 | Other Direct Costs | 56940.35 | 58478.15 | 57685.43 | 57264.59 | 1537.8 | 2.701% | -792.72 | 0.98644
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-11-01 | Labor | 349874.77 | 360711.04 | 357649.12 | 353484.84 | 10836.27 | 3.097% | -3061.92 | 0.99151
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-11-01 | Materials | 272885.05 | 275278.78 | 267789.41 | 278650.14 | 2393.73 | 0.8772% | -7489.37 | 0.97279
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-11-01 | Subcontracts | 213915.45 | 211917.94 | 215938.65 | 211422.71 | -1997.51 | -0.9338% | 4020.71 | 1.019
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-11-01 | Overhead | 158505.42 | 163566.01 | 154301.57 | 163624.37 | 5060.59 | 3.193% | -9264.44 | 0.94336
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-11-01 | Travel | 38343.7 | 38246.73 | 38495.14 | 38861.57 | -96.97 | -0.2529% | 248.41 | 1.0065
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-11-01 | Other Direct Costs | 57155.27 | 55828.09 | 57985.64 | 57269.28 | -1327.18 | -2.322% | 2157.55 | 1.0386
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-12-01 | Labor | 345597.44 | 351243.51 | 339367.61 | 348461.7 | 5646.07 | 1.634% | -11875.9 | 0.96619
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-12-01 | Materials | 281590 | 283462.55 | 276215.66 | 280313.86 | 1872.55 | 0.665% | -7246.89 | 0.97443
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-12-01 | Subcontracts | 219602.7 | 218205.53 | 222937.33 | 219962.5 | -1397.17 | -0.6362% | 4731.8 | 1.0217
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-12-01 | Overhead | 154134.84 | 155361.51 | 158558.42 | 155219.21 | 1226.67 | 0.7958% | 3196.91 | 1.0206
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-12-01 | Travel | 38510.11 | 39277.61 | 38223.75 | 39181.47 | 767.5 | 1.993% | -1053.86 | 0.97317
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2024-12-01 | Other Direct Costs | 59598.66 | 57529.94 | 60554.14 | 58821.83 | -2068.72 | -3.471% | 3024.2 | 1.0526
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-01-01 | Labor | 327941.9 | 322880.74 | 334201.23 | 326583.3 | -5061.16 | -1.543% | 11320.49 | 1.0351
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-01-01 | Materials | 252041.01 | 246780.24 | 248300.3 | 249454.34 | -5260.77 | -2.087% | 1520.06 | 1.0062
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-01-01 | Subcontracts | 203395.87 | 201950.67 | 198701.94 | 200902.35 | -1445.2 | -0.7105% | -3248.73 | 0.98391
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-01-01 | Overhead | 148652.44 | 148970.71 | 150268.05 | 147442.84 | 318.27 | 0.2141% | 1297.34 | 1.0087
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-01-01 | Travel | 36690.99 | 35624.08 | 35613.93 | 36453.52 | -1066.91 | -2.908% | -10.15 | 0.99972
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-01-01 | Other Direct Costs | 55576.43 | 55400.65 | 56048.53 | 55073.85 | -175.78 | -0.3163% | 647.88 | 1.0117
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-02-01 | Labor | 335097.93 | 329297.38 | 334766.34 | 328434.58 | -5800.55 | -1.731% | 5468.96 | 1.0166
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-02-01 | Materials | 259531.84 | 261487.18 | 251947.12 | 260498.68 | 1955.34 | 0.7534% | -9540.06 | 0.96352
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-02-01 | Subcontracts | 213083.34 | 206401.89 | 206897.59 | 206785.23 | -6681.45 | -3.136% | 495.7 | 1.0024
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-02-01 | Overhead | 156425.28 | 157747.94 | 160824.07 | 155652.03 | 1322.66 | 0.8456% | 3076.13 | 1.0195
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-02-01 | Travel | 37413.8 | 37887.41 | 38303.75 | 37704.38 | 473.61 | 1.266% | 416.34 | 1.011
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-02-01 | Other Direct Costs | 54275.26 | 54636.39 | 55768.26 | 54043.94 | 361.13 | 0.6654% | 1131.87 | 1.0207
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-03-01 | Labor | 345639.82 | 347876.82 | 354146.8 | 352250.29 | 2237 | 0.6472% | 6269.98 | 1.018
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-03-01 | Materials | 260502.17 | 257150.3 | 254177.62 | 261534.44 | -3351.87 | -1.287% | -2972.68 | 0.98844
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-03-01 | Subcontracts | 217462.6 | 215219.73 | 217062.61 | 218245.43 | -2242.87 | -1.031% | 1842.88 | 1.0086
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-03-01 | Overhead | 152293.62 | 152873.42 | 149043.24 | 151792.77 | 579.8 | 0.3807% | -3830.18 | 0.97495
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-03-01 | Travel | 35121.71 | 34092.08 | 35311.45 | 34789.77 | -1029.63 | -2.932% | 1219.37 | 1.0358
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-03-01 | Other Direct Costs | 55362.47 | 53950.51 | 56085 | 54700.66 | -1411.96 | -2.55% | 2134.49 | 1.0396
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-04-01 | Labor | 332508.21 | 315409.29 | 342156.41 | 319847.26 | -17098.92 | -5.142% | 26747.12 | 1.0848
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-04-01 | Materials | 260516.58 | 253957.6 | 268157.95 | 255930.14 | -6558.98 | -2.518% | 14200.35 | 1.0559
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-04-01 | Subcontracts | 215530.34 | 207434.18 | 222266.37 | 211171.81 | -8096.16 | -3.756% | 14832.19 | 1.0715
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-04-01 | Overhead | 151132.81 | 140324.01 | 155310.45 | 145630.54 | -10808.8 | -7.152% | 14986.44 | 1.1068
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-04-01 | Travel | 35461.6 | 33771.32 | 35282.38 | 34748 | -1690.28 | -4.767% | 1511.06 | 1.0447
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-04-01 | Other Direct Costs | 55358.76 | 55572.77 | 55849.88 | 55470.12 | 214.01 | 0.3866% | 277.11 | 1.005
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-05-01 | Labor | 339249.43 | 336765.25 | 335985.3 | 334294.61 | -2484.18 | -0.7323% | -779.95 | 0.99768
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-05-01 | Materials | 276744.42 | 269376.59 | 282956.24 | 275673.57 | -7367.83 | -2.662% | 13579.65 | 1.0504
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-05-01 | Subcontracts | 218356.16 | 210028.36 | 220612.75 | 211553.35 | -8327.8 | -3.814% | 10584.39 | 1.0504
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-05-01 | Overhead | 157636.49 | 153988.48 | 164557.38 | 157607.17 | -3648.01 | -2.314% | 10568.9 | 1.0686
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-05-01 | Travel | 37995.18 | 37225.97 | 37488.35 | 37746.85 | -769.21 | -2.024% | 262.38 | 1.007
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-05-01 | Other Direct Costs | 59245.68 | 54431.27 | 58658.55 | 55692.58 | -4814.41 | -8.126% | 4227.28 | 1.0777
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-06-01 | Labor | 351326.9 | 328175.62 | 364240.11 | 332174.65 | -23151.28 | -6.59% | 36064.49 | 1.1099
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-06-01 | Materials | 275666.42 | 265757.02 | 292083.07 | 271528.56 | -9909.4 | -3.595% | 26326.05 | 1.0991
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-06-01 | Subcontracts | 209497.42 | 192980.04 | 211647.33 | 197797.41 | -16517.38 | -7.884% | 18667.29 | 1.0967
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-06-01 | Overhead | 156363.66 | 145321.81 | 156402.76 | 150808.12 | -11041.85 | -7.062% | 11080.95 | 1.0763
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-06-01 | Travel | 38317.35 | 36989.3 | 38457.16 | 38079.49 | -1328.05 | -3.466% | 1467.86 | 1.0397
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-06-01 | Other Direct Costs | 59541.63 | 56371.06 | 60076.06 | 56941.75 | -3170.57 | -5.325% | 3705 | 1.0657
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-07-01 | Labor | 350165.16 | 339381.52 | 353447.03 | 345429.86 | -10783.64 | -3.08% | 14065.51 | 1.0414
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-07-01 | Materials | 272906.81 | 260261.56 | 280181.42 | 265832.12 | -12645.25 | -4.634% | 19919.86 | 1.0765
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-07-01 | Subcontracts | 221935.85 | 205324.81 | 230585.43 | 211668.18 | -16611.04 | -7.485% | 25260.62 | 1.123
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-07-01 | Overhead | 158414.75 | 152797.7 | 165722.27 | 153395.97 | -5617.05 | -3.546% | 12924.57 | 1.0846
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-07-01 | Travel | 37998.22 | 36262.06 | 39197.76 | 37093.93 | -1736.16 | -4.569% | 2935.7 | 1.081
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-07-01 | Other Direct Costs | 60679.13 | 57759.49 | 63453.05 | 59652.13 | -2919.64 | -4.812% | 5693.56 | 1.0986
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-08-01 | Labor | 367712.87 | 345082.44 | 390210.48 | 351712.59 | -22630.43 | -6.154% | 45128.04 | 1.1308
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-08-01 | Materials | 279009.3 | 263382.43 | 281345.18 | 266719.01 | -15626.87 | -5.601% | 17962.75 | 1.0682
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-08-01 | Subcontracts | 216964.04 | 205052.3 | 220578.49 | 212647.08 | -11911.74 | -5.49% | 15526.19 | 1.0757
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-08-01 | Overhead | 163507.95 | 152404.51 | 165322.86 | 155833.73 | -11103.44 | -6.791% | 12918.35 | 1.0848
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-08-01 | Travel | 36737.02 | 34374.22 | 37753.48 | 35405.61 | -2362.8 | -6.432% | 3379.26 | 1.0983
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-08-01 | Other Direct Costs | 59319.42 | 57497.84 | 58284.51 | 57786.2 | -1821.58 | -3.071% | 786.67 | 1.0137
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-09-01 | Labor | 358578.04 | 350493.69 | 374618.47 | 356305.27 | -8084.35 | -2.255% | 24124.78 | 1.0688
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-09-01 | Materials | 288988.65 | 282923.09 | 290446.1 | 283677.55 | -6065.56 | -2.099% | 7523.01 | 1.0266
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-09-01 | Subcontracts | 221456.83 | 218817.03 | 225941.93 | 220848.36 | -2639.8 | -1.192% | 7124.9 | 1.0326
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-09-01 | Overhead | 156981.46 | 152555.79 | 162958.57 | 155251.89 | -4425.67 | -2.819% | 10402.78 | 1.0682
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-09-01 | Travel | 38616.09 | 38707.65 | 38915.6 | 38713.98 | 91.56 | 0.2371% | 207.95 | 1.0054
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-09-01 | Other Direct Costs | 59781.66 | 58495.99 | 58628.42 | 58669.19 | -1285.67 | -2.151% | 132.43 | 1.0023
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-10-01 | Labor | 361343.91 | 348177.67 | 375092.61 | 349869.62 | -13166.24 | -3.644% | 26914.94 | 1.0773
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-10-01 | Materials | 273735.45 | 265343.97 | 279381.3 | 266212.89 | -8391.48 | -3.066% | 14037.33 | 1.0529
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-10-01 | Subcontracts | 216383.08 | 207627.25 | 220054.56 | 208098.78 | -8755.83 | -4.046% | 12427.31 | 1.0599
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-10-01 | Overhead | 160142.18 | 153022.09 | 169408.95 | 154137.82 | -7120.09 | -4.446% | 16386.86 | 1.1071
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-10-01 | Travel | 38935.35 | 38286.83 | 40427.35 | 38575.28 | -648.52 | -1.666% | 2140.52 | 1.0559
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-10-01 | Other Direct Costs | 58525.65 | 55278.63 | 60899.36 | 57226.62 | -3247.02 | -5.548% | 5620.73 | 1.1017
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-11-01 | Labor | 350792.07 | 334627.1 | 362717.1 | 344310.81 | -16164.97 | -4.608% | 28090 | 1.0839
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-11-01 | Materials | 291362.92 | 281173.44 | 289624.45 | 286050.03 | -10189.48 | -3.497% | 8451.01 | 1.0301
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-11-01 | Subcontracts | 220079.85 | 208177.04 | 222774.94 | 214520.36 | -11902.81 | -5.408% | 14597.9 | 1.0701
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-11-01 | Overhead | 167896.55 | 155495.96 | 177904.47 | 162475.72 | -12400.59 | -7.386% | 22408.51 | 1.1441
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-11-01 | Travel | 40089.33 | 37607.26 | 40250.21 | 39129.65 | -2482.07 | -6.191% | 2642.95 | 1.0703
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-11-01 | Other Direct Costs | 62646.86 | 61219.43 | 61822.03 | 61269.29 | -1427.43 | -2.279% | 602.6 | 1.0098
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-12-01 | Labor | 379465.44 | 350779.08 | 394611.8 | 357829.54 | -28686.36 | -7.56% | 43832.72 | 1.125
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-12-01 | Materials | 289303.98 | 270304.94 | 291215.08 | 280806.14 | -18999.04 | -6.567% | 20910.14 | 1.0774
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-12-01 | Subcontracts | 222066.94 | 208822.09 | 234917.98 | 215760.11 | -13244.85 | -5.964% | 26095.89 | 1.125
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-12-01 | Overhead | 164111.46 | 152392.02 | 166818.45 | 158516.56 | -11719.44 | -7.141% | 14426.43 | 1.0947
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-12-01 | Travel | 38157.6 | 35507.33 | 38873.41 | 35980.62 | -2650.27 | -6.946% | 3366.08 | 1.0948
AP-105 | Vanguard | DoD | Autonomous Systems | Priya Shah | 2025-12-01 | Other Direct Costs | 60518.41 | 57713.7 | 61174.51 | 59680.95 | -2804.71 | -4.634% | 3460.81 | 1.06
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-01-01 | Labor | 438710.98 | 444839.47 | 425563.65 | 443252.9 | 6128.49 | 1.397% | -19275.82 | 0.95667
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-01-01 | Materials | 345803.53 | 336357.05 | 342717.29 | 343953.93 | -9446.48 | -2.732% | 6360.24 | 1.0189
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-01-01 | Subcontracts | 282234.73 | 278230.64 | 274799.28 | 280911.82 | -4004.09 | -1.419% | -3431.36 | 0.98767
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-01-01 | Overhead | 208057.72 | 206590.88 | 210247.76 | 210158.12 | -1466.84 | -0.705% | 3656.88 | 1.0177
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-01-01 | Travel | 48721.36 | 48130.13 | 49914.48 | 49024.44 | -591.23 | -1.213% | 1784.35 | 1.0371
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-01-01 | Other Direct Costs | 72547.24 | 73014.11 | 73304.84 | 73804.47 | 466.87 | 0.6435% | 290.73 | 1.004
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-02-01 | Labor | 466621.06 | 480069.27 | 466982.11 | 483580.93 | 13448.21 | 2.882% | -13087.16 | 0.97274
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-02-01 | Materials | 348587.72 | 343674.67 | 343840.71 | 346505.31 | -4913.05 | -1.409% | 166.04 | 1.0005
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-02-01 | Subcontracts | 269691.1 | 264039.13 | 274821.26 | 268273.98 | -5651.97 | -2.096% | 10782.13 | 1.0408
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-02-01 | Overhead | 201764.74 | 207007.03 | 200329.55 | 203397.61 | 5242.29 | 2.598% | -6677.48 | 0.96774
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-02-01 | Travel | 48913.58 | 47699.01 | 49780.38 | 48848.38 | -1214.57 | -2.483% | 2081.37 | 1.0436
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-02-01 | Other Direct Costs | 77677.34 | 76137.23 | 75501.94 | 77112.65 | -1540.11 | -1.983% | -635.29 | 0.99166
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-03-01 | Labor | 447233.84 | 459017.16 | 436978.15 | 449751.36 | 11783.32 | 2.635% | -22039.01 | 0.95199
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-03-01 | Materials | 365979.77 | 362991.16 | 361021.29 | 366012.67 | -2988.61 | -0.8166% | -1969.87 | 0.99457
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-03-01 | Subcontracts | 272603.44 | 269784.55 | 268815.34 | 272197.47 | -2818.89 | -1.034% | -969.21 | 0.99641
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-03-01 | Overhead | 206755.08 | 206143.31 | 206748.68 | 204823.22 | -611.77 | -0.2959% | 605.37 | 1.0029
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-03-01 | Travel | 50653.16 | 50506.07 | 51612.56 | 51042.46 | -147.09 | -0.2904% | 1106.49 | 1.0219
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-03-01 | Other Direct Costs | 77354.63 | 76708.95 | 77895.54 | 76460.09 | -645.68 | -0.8347% | 1186.59 | 1.0155
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-04-01 | Labor | 477934.15 | 475531.03 | 465571.69 | 475114.57 | -2403.12 | -0.5028% | -9959.34 | 0.97906
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-04-01 | Materials | 358464.49 | 348022.65 | 358973.06 | 350191.58 | -10441.84 | -2.913% | 10950.41 | 1.0315
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-04-01 | Subcontracts | 281254.21 | 273177.3 | 287713.8 | 274881.46 | -8076.91 | -2.872% | 14536.5 | 1.0532
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-04-01 | Overhead | 209197.51 | 212306.32 | 210736.14 | 214659.94 | 3108.81 | 1.486% | -1570.18 | 0.9926
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-04-01 | Travel | 48472.76 | 48264.11 | 49508.13 | 48206.75 | -208.65 | -0.4304% | 1244.02 | 1.0258
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-04-01 | Other Direct Costs | 75725 | 77379.6 | 73957.18 | 78079.59 | 1654.6 | 2.185% | -3422.42 | 0.95577
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-05-01 | Labor | 465829.01 | 451549.22 | 479788.3 | 451529.7 | -14279.79 | -3.065% | 28239.08 | 1.0625
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-05-01 | Materials | 372103.59 | 374381.7 | 382165.57 | 375534.04 | 2278.11 | 0.6122% | 7783.87 | 1.0208
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-05-01 | Subcontracts | 278988.98 | 272441.93 | 282718.98 | 279049.42 | -6547.05 | -2.347% | 10277.05 | 1.0377
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-05-01 | Overhead | 214884.79 | 212496.96 | 214435.8 | 215880.21 | -2387.83 | -1.111% | 1938.84 | 1.0091
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-05-01 | Travel | 50371.81 | 51236.9 | 49505.36 | 50885.42 | 865.09 | 1.717% | -1731.54 | 0.96621
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-05-01 | Other Direct Costs | 77874.51 | 80208.13 | 79765.29 | 79010.29 | 2333.62 | 2.997% | -442.84 | 0.99448
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-06-01 | Labor | 463922.08 | 478945.82 | 472197.3 | 475719.56 | 15023.74 | 3.238% | -6748.52 | 0.98591
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-06-01 | Materials | 379173.47 | 376343.29 | 373430.94 | 383989.53 | -2830.18 | -0.7464% | -2912.35 | 0.99226
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-06-01 | Subcontracts | 290719.54 | 293280.76 | 289332.46 | 296543.42 | 2561.22 | 0.881% | -3948.3 | 0.98654
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-06-01 | Overhead | 213719.38 | 211674.16 | 213084.79 | 214077.98 | -2045.22 | -0.957% | 1410.63 | 1.0067
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-06-01 | Travel | 51631.03 | 51465.8 | 52843.48 | 51842.18 | -165.23 | -0.32% | 1377.68 | 1.0268
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-06-01 | Other Direct Costs | 77814.31 | 80394.43 | 79534.26 | 80371.25 | 2580.12 | 3.316% | -860.17 | 0.9893
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-07-01 | Labor | 462733.62 | 455030.2 | 476043.11 | 460619.53 | -7703.42 | -1.665% | 21012.91 | 1.0462
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-07-01 | Materials | 364668.39 | 361543.59 | 356921.46 | 363049.53 | -3124.8 | -0.8569% | -4622.13 | 0.98722
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-07-01 | Subcontracts | 302291.1 | 304632.36 | 300043.69 | 306025.12 | 2341.26 | 0.7745% | -4588.67 | 0.98494
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-07-01 | Overhead | 210058.53 | 212949.07 | 205977.83 | 210790.18 | 2890.54 | 1.376% | -6971.24 | 0.96726
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-07-01 | Travel | 48968.95 | 49869.5 | 49568.52 | 50370.58 | 900.55 | 1.839% | -300.98 | 0.99396
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-07-01 | Other Direct Costs | 78743.9 | 78897.79 | 77943.37 | 80033.74 | 153.89 | 0.1954% | -954.42 | 0.9879
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-08-01 | Labor | 473440.09 | 476353.16 | 477927.57 | 471622.62 | 2913.07 | 0.6153% | 1574.41 | 1.0033
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-08-01 | Materials | 390468.3 | 389994.63 | 395057.31 | 389112.9 | -473.67 | -0.1213% | 5062.68 | 1.013
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-08-01 | Subcontracts | 302403.57 | 308864.21 | 298809.92 | 306762.79 | 6460.64 | 2.136% | -10054.29 | 0.96745
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-08-01 | Overhead | 223124.73 | 228838.15 | 223157.75 | 225968.94 | 5713.42 | 2.561% | -5680.4 | 0.97518
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-08-01 | Travel | 53147.92 | 52152.36 | 51857.25 | 53184.3 | -995.56 | -1.873% | -295.11 | 0.99434
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-08-01 | Other Direct Costs | 79387.07 | 77540.36 | 81305.86 | 78635 | -1846.71 | -2.326% | 3765.5 | 1.0486
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-09-01 | Labor | 467584.08 | 451848.25 | 462137.7 | 453424.07 | -15735.83 | -3.365% | 10289.45 | 1.0228
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-09-01 | Materials | 380889.99 | 383024.11 | 370970.8 | 388295.2 | 2134.12 | 0.5603% | -12053.31 | 0.96853
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-09-01 | Subcontracts | 287814.94 | 295436.84 | 280949.57 | 290720.14 | 7621.9 | 2.648% | -14487.27 | 0.95096
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-09-01 | Overhead | 212206.81 | 209237.31 | 215279.46 | 213277.06 | -2969.5 | -1.399% | 6042.15 | 1.0289
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-09-01 | Travel | 53691.75 | 52705.44 | 55075.15 | 53919.82 | -986.31 | -1.837% | 2369.71 | 1.045
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-09-01 | Other Direct Costs | 82437.8 | 81965.57 | 81700.3 | 81520.03 | -472.23 | -0.5728% | -265.27 | 0.99676
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-10-01 | Labor | 491620.04 | 506816.54 | 502882.27 | 501037.69 | 15196.5 | 3.091% | -3934.27 | 0.99224
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-10-01 | Materials | 371346.37 | 370169.87 | 368307.24 | 374242.33 | -1176.5 | -0.3168% | -1862.63 | 0.99497
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-10-01 | Subcontracts | 292279.76 | 292885.93 | 284924.89 | 291154.11 | 606.17 | 0.2074% | -7961.04 | 0.97282
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-10-01 | Overhead | 216066.12 | 215345.95 | 211892.63 | 215928.19 | -720.17 | -0.3333% | -3453.32 | 0.98396
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-10-01 | Travel | 52979.38 | 52615.26 | 53573.71 | 53172.04 | -364.12 | -0.6873% | 958.45 | 1.0182
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-10-01 | Other Direct Costs | 81970.77 | 83656.22 | 80381.44 | 83982.26 | 1685.45 | 2.056% | -3274.78 | 0.96085
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-11-01 | Labor | 503720.01 | 510629.05 | 492073.55 | 515111.67 | 6909.04 | 1.372% | -18555.5 | 0.96366
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-11-01 | Materials | 373963.87 | 367678.38 | 378189.5 | 367536.24 | -6285.49 | -1.681% | 10511.12 | 1.0286
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-11-01 | Subcontracts | 311813.31 | 308139.5 | 316565.43 | 306868.04 | -3673.81 | -1.178% | 8425.93 | 1.0273
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-11-01 | Overhead | 217613.95 | 214114.91 | 218129.3 | 215214.03 | -3499.04 | -1.608% | 4014.39 | 1.0187
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-11-01 | Travel | 53293.97 | 53009.65 | 53230.33 | 53524.43 | -284.32 | -0.5335% | 220.68 | 1.0042
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-11-01 | Other Direct Costs | 83953.75 | 82169.89 | 85542.58 | 82466.8 | -1783.86 | -2.125% | 3372.69 | 1.041
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-12-01 | Labor | 490128.04 | 477339.86 | 481831.51 | 484251.96 | -12788.18 | -2.609% | 4491.65 | 1.0094
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-12-01 | Materials | 403116.89 | 389706.54 | 414857.64 | 398399.61 | -13410.35 | -3.327% | 25151.1 | 1.0645
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-12-01 | Subcontracts | 299252.96 | 299438.47 | 306726.61 | 300234.99 | 185.51 | 0.06199% | 7288.14 | 1.0243
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-12-01 | Overhead | 219877.55 | 216764.39 | 224242.26 | 220406.11 | -3113.16 | -1.416% | 7477.87 | 1.0345
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-12-01 | Travel | 53659.06 | 53213.01 | 52881.88 | 53524.29 | -446.05 | -0.8313% | -331.13 | 0.99378
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2024-12-01 | Other Direct Costs | 84481.38 | 85302.08 | 82880.97 | 85138.5 | 820.7 | 0.9715% | -2421.11 | 0.97162
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-01-01 | Labor | 481720.05 | 465628.95 | 475187.66 | 477221.47 | -16091.1 | -3.34% | 9558.71 | 1.0205
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-01-01 | Materials | 382568.9 | 371100.51 | 392593.61 | 381062.89 | -11468.39 | -2.998% | 21493.1 | 1.0579
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-01-01 | Subcontracts | 297002.11 | 290083.56 | 293810.1 | 292335.59 | -6918.55 | -2.329% | 3726.54 | 1.0128
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-01-01 | Overhead | 205992.63 | 212745.42 | 202480.18 | 212331.36 | 6752.79 | 3.278% | -10265.24 | 0.95175
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-01-01 | Travel | 48698.05 | 48700.21 | 48410.01 | 49278.74 | 2.16 | 0.004435% | -290.2 | 0.99404
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-01-01 | Other Direct Costs | 75885.64 | 78333.89 | 75438.14 | 78640.05 | 2448.25 | 3.226% | -2895.75 | 0.96303
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-02-01 | Labor | 467431.17 | 478853.82 | 459010.76 | 483043.65 | 11422.65 | 2.444% | -19843.06 | 0.95856
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-02-01 | Materials | 372844.08 | 377515.92 | 366554.68 | 378203 | 4671.84 | 1.253% | -10961.24 | 0.97096
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-02-01 | Subcontracts | 290589.86 | 300297.48 | 293063.24 | 298957.56 | 9707.62 | 3.341% | -7234.24 | 0.97591
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-02-01 | Overhead | 217683.5 | 216344.7 | 217959.55 | 214817.34 | -1338.8 | -0.615% | 1614.85 | 1.0075
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-02-01 | Travel | 49960.49 | 51099.42 | 51352.91 | 50741.51 | 1138.93 | 2.28% | 253.49 | 1.005
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-02-01 | Other Direct Costs | 77854.91 | 80329.3 | 77114.05 | 80500.69 | 2474.39 | 3.178% | -3215.25 | 0.95997
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-03-01 | Labor | 466126 | 459136.44 | 467939.42 | 462095.26 | -6989.56 | -1.5% | 8802.98 | 1.0192
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-03-01 | Materials | 384122.5 | 389168.14 | 380413.7 | 389963.93 | 5045.64 | 1.314% | -8754.44 | 0.9775
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-03-01 | Subcontracts | 286317.1 | 307368.82 | 293863.52 | 296745.99 | 21051.72 | 7.353% | -13505.3 | 0.95606
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-03-01 | Overhead | 210896.75 | 217224.15 | 207423.04 | 212800.12 | 6327.4 | 3% | -9801.11 | 0.95488
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-03-01 | Travel | 51547.99 | 53175.51 | 52848.13 | 53273.65 | 1627.52 | 3.157% | -327.38 | 0.99384
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-03-01 | Other Direct Costs | 77268.83 | 78607.55 | 78539.58 | 77679.6 | 1338.72 | 1.733% | -67.97 | 0.99914
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-04-01 | Labor | 492019.6 | 482072.75 | 483566.12 | 480247.12 | -9946.85 | -2.022% | 1493.37 | 1.0031
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-04-01 | Materials | 383635.04 | 387358.78 | 381805.74 | 390411.59 | 3723.74 | 0.9706% | -5553.04 | 0.98566
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-04-01 | Subcontracts | 298413.49 | 324629.63 | 305941.81 | 320678.99 | 26216.14 | 8.785% | -18687.82 | 0.94243
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-04-01 | Overhead | 214883.01 | 212605.68 | 220047.89 | 215000.43 | -2277.33 | -1.06% | 7442.21 | 1.035
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-04-01 | Travel | 50359.46 | 52106.68 | 49361.59 | 51152.33 | 1747.22 | 3.469% | -2745.09 | 0.94732
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-04-01 | Other Direct Costs | 82453.51 | 81066.09 | 83235.86 | 81125.39 | -1387.42 | -1.683% | 2169.77 | 1.0268
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-05-01 | Labor | 504885.07 | 507814.5 | 503023.73 | 507793.14 | 2929.43 | 0.5802% | -4790.77 | 0.99057
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-05-01 | Materials | 396064.01 | 385352.67 | 389801.03 | 394867.81 | -10711.34 | -2.704% | 4448.36 | 1.0115
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-05-01 | Subcontracts | 293347.18 | 304513.31 | 286394.36 | 297509.11 | 11166.13 | 3.806% | -18118.95 | 0.9405
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-05-01 | Overhead | 212584.12 | 211228.6 | 215673.6 | 214759.55 | -1355.52 | -0.6376% | 4445 | 1.021
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-05-01 | Travel | 53870.33 | 53521.54 | 52278.38 | 54373.77 | -348.79 | -0.6475% | -1243.16 | 0.97677
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-05-01 | Other Direct Costs | 80290.34 | 81629.66 | 78561.18 | 80870.51 | 1339.32 | 1.668% | -3068.48 | 0.96241
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-06-01 | Labor | 505548.84 | 507311.09 | 513149.71 | 503115.38 | 1762.25 | 0.3486% | 5838.62 | 1.0115
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-06-01 | Materials | 396932.6 | 409122.9 | 406736.15 | 409158.11 | 12190.3 | 3.071% | -2386.75 | 0.99417
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-06-01 | Subcontracts | 314099.2 | 340637.84 | 312857.55 | 330973.15 | 26538.64 | 8.449% | -27780.29 | 0.91845
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-06-01 | Overhead | 222846.07 | 224040.06 | 223751.7 | 226129.81 | 1193.99 | 0.5358% | -288.36 | 0.99871
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-06-01 | Travel | 52857.39 | 54110.68 | 52442.19 | 53468.22 | 1253.29 | 2.371% | -1668.49 | 0.96917
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-06-01 | Other Direct Costs | 85058.9 | 82142.28 | 84840.87 | 83703.54 | -2916.62 | -3.429% | 2698.59 | 1.0329
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-07-01 | Labor | 500334.66 | 513608.07 | 496832.47 | 509224.7 | 13273.41 | 2.653% | -16775.6 | 0.96734
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-07-01 | Materials | 404392.89 | 400858.68 | 408811.75 | 403057.31 | -3534.21 | -0.874% | 7953.07 | 1.0198
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-07-01 | Subcontracts | 310176.83 | 334120.68 | 304171.55 | 329597.18 | 23943.85 | 7.719% | -29949.13 | 0.91036
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-07-01 | Overhead | 219355.62 | 224350.47 | 214664.69 | 225214.91 | 4994.85 | 2.277% | -9685.78 | 0.95683
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-07-01 | Travel | 53587.69 | 53030.91 | 53767.46 | 53336.89 | -556.78 | -1.039% | 736.55 | 1.0139
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-07-01 | Other Direct Costs | 85937.07 | 83462.16 | 86510.52 | 83647.88 | -2474.91 | -2.88% | 3048.36 | 1.0365
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-08-01 | Labor | 483135.78 | 488835.59 | 480630.81 | 484483.72 | 5699.81 | 1.18% | -8204.78 | 0.98322
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-08-01 | Materials | 385886.81 | 372548.6 | 393357.53 | 383704.93 | -13338.21 | -3.457% | 20808.93 | 1.0559
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-08-01 | Subcontracts | 304824.31 | 329927.09 | 297164.14 | 325653.88 | 25102.78 | 8.235% | -32762.95 | 0.9007
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-08-01 | Overhead | 232929.04 | 229581.23 | 226363.47 | 233527.83 | -3347.81 | -1.437% | -3217.76 | 0.98598
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-08-01 | Travel | 52018.07 | 53833.5 | 51619.15 | 52666.08 | 1815.43 | 3.49% | -2214.35 | 0.95887
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-08-01 | Other Direct Costs | 86392.11 | 86052.96 | 87342.03 | 85191.73 | -339.15 | -0.3926% | 1289.07 | 1.015
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-09-01 | Labor | 520036.75 | 503553.7 | 522494.13 | 506533.61 | -16483.05 | -3.17% | 18940.43 | 1.0376
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-09-01 | Materials | 400501.58 | 414315.19 | 394157.86 | 405351.13 | 13813.61 | 3.449% | -20157.33 | 0.95135
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-09-01 | Subcontracts | 318745.67 | 352314.96 | 314199.7 | 338988.97 | 33569.29 | 10.53% | -38115.26 | 0.89181
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-09-01 | Overhead | 224905.25 | 220246.62 | 229004.59 | 224072.87 | -4658.63 | -2.071% | 8757.97 | 1.0398
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-09-01 | Travel | 56067.62 | 55624.07 | 55309.04 | 56464.93 | -443.55 | -0.7911% | -315.03 | 0.99434
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-09-01 | Other Direct Costs | 86053.66 | 86972.33 | 83620.37 | 86861.06 | 918.67 | 1.068% | -3351.96 | 0.96146
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-10-01 | Labor | 492262.22 | 495550.3 | 505433.99 | 492011.28 | 3288.08 | 0.668% | 9883.69 | 1.0199
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-10-01 | Materials | 398723.21 | 406764.16 | 388025.64 | 402004.3 | 8040.95 | 2.017% | -18738.52 | 0.95393
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-10-01 | Subcontracts | 317122.64 | 342097.36 | 309011.56 | 338179.06 | 24974.72 | 7.875% | -33085.8 | 0.90329
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-10-01 | Overhead | 226177.72 | 220862.19 | 232441.48 | 222081.69 | -5315.53 | -2.35% | 11579.29 | 1.0524
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-10-01 | Travel | 56477.17 | 57711.17 | 55540.43 | 58137.04 | 1234 | 2.185% | -2170.74 | 0.96239
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-10-01 | Other Direct Costs | 86996.68 | 86356.43 | 85438.35 | 87333.55 | -640.25 | -0.7359% | -918.08 | 0.98937
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-11-01 | Labor | 525527.71 | 507918.32 | 532100.39 | 518398.93 | -17609.39 | -3.351% | 24182.07 | 1.0476
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-11-01 | Materials | 417065.41 | 405595.86 | 418781.38 | 410235.71 | -11469.55 | -2.75% | 13185.52 | 1.0325
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-11-01 | Subcontracts | 330665.68 | 364807.99 | 323348.67 | 349446.07 | 34142.31 | 10.33% | -41459.32 | 0.88635
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-11-01 | Overhead | 242029.46 | 239549.46 | 243098.14 | 241663.35 | -2480 | -1.025% | 3548.68 | 1.0148
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-11-01 | Travel | 55979.94 | 56377.03 | 56972.69 | 56211.93 | 397.09 | 0.7093% | 595.66 | 1.0106
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-11-01 | Other Direct Costs | 86217.51 | 84650.53 | 85735.19 | 84938.68 | -1566.98 | -1.817% | 1084.66 | 1.0128
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-12-01 | Labor | 520422.1 | 529125.84 | 515279.64 | 533201.91 | 8703.74 | 1.672% | -13846.2 | 0.97383
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-12-01 | Materials | 394819.89 | 400912.69 | 401660.38 | 402737.95 | 6092.8 | 1.543% | 747.69 | 1.0019
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-12-01 | Subcontracts | 314394.08 | 338063.75 | 305634.29 | 331001.6 | 23669.67 | 7.529% | -32429.46 | 0.90407
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-12-01 | Overhead | 232125.51 | 225265.15 | 226470.68 | 225608.8 | -6860.36 | -2.955% | 1205.53 | 1.0054
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-12-01 | Travel | 54446.08 | 54715.06 | 54988.81 | 54826.24 | 268.98 | 0.494% | 273.75 | 1.005
AP-106 | Horizon | Commercial | Aircraft | Michael Grant | 2025-12-01 | Other Direct Costs | 89912.55 | 88582.65 | 88618.04 | 88309.73 | -1329.9 | -1.479% | 35.39 | 1.0004

## Excel_Analysis
Row Labels | Sum of budget_cost | Sum of actual_cost | Sum of budget_variance | Sum of budget_variance | Column Labels
Atlas | 29736333.53 | 29664283.81 | -72049.72 | Row Labels | Labor | Materials | Other Direct Costs | Overhead | Subcontracts | Travel | Grand Total
Falcon | 41164053.12 | 41118843.01 | -45210.11 | Atlas | 36989.72 | -81192.85 | 9632.95 | -13327.07 | -24235.7 | 83.23 | -72049.72
Horizon | 36344496.05 | 36535039.61 | 190543.56 | Falcon | 29424.6 | -19001.88 | -713.71 | 7274.33 | -56807.74 | -5385.71 | -45210.11
Orion | 44623501.77 | 46181194.26 | 1557692.49 | Horizon | -1548.55 | -47621.56 | 1270.78 | -8223.42 | 242168.3 | 4498.01 | 190543.56
Sentinel | 34648455.8 | 35536094.5 | 887638.7 | Orion | 76970.8 | 1068740.1 | 5722.97 | 25866.23 | 373774.75 | 6617.64 | 1557692.49
Vanguard | 25672035.61 | 25774871.58 | 102835.97 | Sentinel | 845459.17 | -16287.36 | 7563.41 | 11991.12 | 37229.25 | 1683.11 | 887638.7
Grand Total | 212188875.88 | 214810326.77 | 2621450.89 | Vanguard | 23278.22 | 49331.39 | 3978.66 | 16760.18 | 7175.86 | 2311.66 | 102835.97
|  |  |  | Grand Total | 1010573.96 | 953967.84 | 27455.06 | 40341.37 | 579304.72 | 9807.94 | 2621450.89
program_name | Sentinel
cost_category | Labor
Row Labels | Sum of budget_variance
2024-01-01 | 14249.54
2024-02-01 | -2712.89
2024-03-01 | -6882.01
2024-04-01 | 15440.14
2024-05-01 | 13023.9
2024-06-01 | -3017.15
2024-07-01 | -2049.28
2024-08-01 | 39273.13
2024-09-01 | 45169.53
2024-10-01 | 27689.4
2024-11-01 | 30836.39
2024-12-01 | 27336.7
2025-01-01 | 33499.78
2025-02-01 | 44220.07
2025-03-01 | 37685.85
2025-04-01 | 47587.52
2025-05-01 | 40761.56
2025-06-01 | 56389.91
2025-07-01 | 54267.78
2025-08-01 | 72502.69
2025-09-01 | 50980.65
2025-10-01 | 64492.13
2025-11-01 | 73842.89
2025-12-01 | 70870.94
Grand Total | 845459.17
Preliminary Financial Analysis — Key Findings
1. Portfolio performance The six-program portfolio finished approximately $2.62M over budget across the reporting period.
2. Primary programs requiring attention Orion and Sentinel were the primary drivers of unfavorable portfolio cost variance, with total budget variances of approximately $1.56M and $888K, respectively.
3. Orion variance driver Orion's performance was primarily driven by Materials, which generated approximately $1.07M in unfavorable variance. The sustained Materials overrun began in June 2024 and persisted through the remainder of the reporting period.
4. Sentinel variance driver Sentinel's performance was primarily driven by Labor, which generated approximately $845K in unfavorable variance. The sustained Labor overrun began in August 2024 and persisted through the remainder of the reporting period.